EiBS  •  ELYSIAN INTELLIGENCE BUSINESS SOLUTIONS

Enterprise Software Engineering  •  ERP & Platform Delivery

DELIVERY WORKFLOW SYSTEM

SAIGEN — Enterprise ERP & Multi-Tenant SaaS Platform

A production-ready, execution-level workflow derived from the SAIGEN

Project Development Document (PDD v1.0) — structured for Jira / Notion / ClickUp

| Document | SAIGEN Delivery Workflow System |
| --- | --- |
| Source baseline | Project Development Document (PDD) v1.0 |
| Delivery partner | EiBS — Elysian Intelligence Business Solutions Pvt. Ltd. |
| Product owner | Elysium Groups / Elysium Technologies Pvt. Ltd. |
| Functional footprint | 16 published modules + AI layer + cross-cutting platform |
| Classification | Confidential — Client & Internal Use |
| Status | Issued for delivery planning |

# Table of Contents

# 0.  How to Use This Workflow

This document converts the SAIGEN PDD into an executable delivery workflow. It is organised so a cross-functional team (product, engineering, design, QA, DevOps and operations) can implement SAIGEN without re-interpreting the source specification. Every workflow task carries a stable Task ID (WF-[phase].[n]) and maps back to the PDD functional requirements (FR-…), non-functional requirements (NFR-…), milestones (M0–M5) and acceptance criteria (AC-…) so traceability is preserved end-to-end.

Reading guide Section 1–2 set the charter and the high-level phase architecture. Section 3 is the deep task backlog — each block is import-ready for Jira/Notion/ClickUp (Description, Inputs, Outputs, Owner, Tools, Effort, Priority). Section 4–5 define sequencing, the critical path, and ownership (RACI). Section 6–9 cover risk, automation, timeline and the handoff checklist.

# 1.  Project Overview

## 1.1  Project Name

SAIGEN — Enterprise ERP & Multi-Tenant SaaS Platform. A cloud-native, API-first, schema-isolated multi-tenant ERP unifying eight core operational disciplines plus multi-branch consolidation, subscription billing, a public SaaS landing page and an embedded AI Suggestions layer (16 published modules in total).

## 1.2  Core Objective

Deliver, in phased increments, a single integrated system of record that eliminates double data entry across finance, CRM/sales, supply chain, assets, service, human capital and administration; provides per-branch P&L with group-level consolidation; and ships the commercial machinery (tiered plans, metered seats, multi-gateway billing, automated tenant provisioning) needed to operate SAIGEN as a productised SaaS.

Primary objectives carried from the PDD

| Obj. ID | Objective | Success indicator |
| --- | --- | --- |
| OBJ-01 | Unified multi-tenant ERP across the eight core modules. | All in-scope modules deployed and UAT-accepted. |
| OBJ-02 | Eliminate double entry via cross-module integration. | Customer/product/employee maintained once, shared. |
| OBJ-03 | Multi-branch operation with consolidated reporting. | Per-branch P&L + Group Executive Dashboard live. |
| OBJ-04 | SaaS commercialisation with tiered, automated billing. | Four tiers live with provisioning, metering, gateways. |
| OBJ-05 | AI-driven, actionable cross-module recommendations. | AI panel live, refreshed and impact-ranked. |
| OBJ-06 | Role- and branch-scoped access with auditability. | RBAC enforced; access events logged and reviewable. |

## 1.3  Key Deliverables

- Foundation platform — identity/MFA, schema-per-tenant multi-tenancy, RBAC + branch scoping, audit log and observability baseline.

- Eight core ERP modules — Executive Overview (EXO), Financial Systems (FIN), CRM & Sales (CRM), Supply Chain (SCM), Asset Management (AST), Ticket Management (TKT), Human Capital (HCM), Administration (ADM).

- Commercial platform — Multi-Branch Management (BRN), Subscription & Billing (SUB) with Stripe/PayPal/Razorpay, automated workspace provisioning, and the public SaaS Landing Page (LP).

- Intelligence layer — cross-module AI Suggestions engine with impact ranking and deep-linking.

- Cross-cutting platform services — API-first contracts, multi-currency/FX, calendar/email integration, secrets management.

- Delivery artefacts — detailed design, FR/NFR traceability matrix, test suites & reports, deployment runbook + rollback, UAT acceptance records, and operations handover to the AMC support model.

## 1.4  Success Metrics (KPIs)

KPIs are split into delivery-health metrics (tracked throughout execution) and product-quality targets (verified at hardening/UAT against the PDD NFRs and acceptance criteria).

Product-quality targets

| KPI | Target | Source / verified by |
| --- | --- | --- |
| Production availability | 99.9% uptime per calendar month (tier-configurable) | NFR-01 / AC-07 |
| Page render latency | Core interactive pages < 2 s at p95 under load | NFR-02 / AC-07 |
| API latency | Standard API responses < 500 ms | NFR-02 |
| Recovery objectives | RPO ≤ 1 hour, RTO ≤ 4 hours | NFR-10 / AC-10 |
| Tenant isolation | Zero cross-tenant data exposure under any path | NFR-04 / AC-03 |
| Accessibility | WCAG 2.1 AA on primary journeys | NFR-09 |
| Functional completeness | 100% of Must-priority FRs pass system test | AC-01 |
| Integration integrity | Cross-module workflows operate with zero re-entry | AC-02 |
| Defect exit bar | No open Critical/High defects at final acceptance | AC-09 / Sec. 17 |

Delivery-health metrics

- Milestone gate adherence — M0–M5 accepted on or before their planned gate dates.

- Requirements traceability — 100% of FRs mapped to a workflow task, a test case and an acceptance criterion.

- Sprint predictability — planned-vs-delivered story points within ±15% per sprint.

- Quality-gate pass rate — smoke + regression suites green before every promotion to Staging.

- Client-dependency SLA — sign-offs, master data and gateway accounts delivered within agreed lead times (see Risk R-04).

# 2.  Workflow Architecture (High-Level Phases)

The delivery lifecycle is expressed as six standard phases (Discovery/Planning → Design → Development → Testing → Deployment → Post-Launch Optimisation) overlaid on the PDD's phased plan (Phase 0–7) and milestone gates (M0–M5). Development is value-sequenced into four sub-increments so the team releases working capability early and de-risks the most complex modules last.

## 2.1  Phase Map

| Lifecycle phase | PDD phase(s) | Milestone | Outcome anchor |
| --- | --- | --- | --- |
| Discovery / Planning | Phase 0 | M0 — Baseline | Signed PDD, detailed design, environments + pipeline ready. |
| Design | Phase 0 (cont.) | M0 | Architecture baseline, data model, API contracts, UX system. |
| Development — Essentials | Phase 1 | M1 — Essentials | Identity, tenancy, RBAC, Executive Overview, CRM Essentials. |
| Development — Finance & Sales | Phase 2 | M2 — Sales | Finance core + full CRM/Sales with multi-currency. |
| Development — Operations | Phase 3 | M3 — Operations | Supply Chain, Assets, Ticket/Service. |
| Development — People & Admin | Phase 4 | (rolls to M4) | HCM, Administration, System Settings. |
| Development — Commercialisation | Phase 5 | M4 — Commercial | Multi-Branch, Subscription/Billing, gateways, landing page, AI engine. |
| Testing / Hardening | Phase 6 | (gates M5) | Security, performance, system/regression, UAT, defect closure. |
| Deployment | Phase 7 | M5 — Go-Live | Production cut-over, hyper-care. |
| Post-Launch Optimisation | Post Phase 7 | Post-M5 | Hyper-care exit, AMC support, AI tuning, enhancement intake. |

## 2.2  Phase Purpose & Key Outcomes

Discovery / Planning

Purpose. Lock the contractual baseline and remove ambiguity before build. Establish governance, environments and the delivery toolchain.

Key outcomes:

- PDD signed (M0); change-control, RACI and risk register active.

- Dev/QA/Staging/Prod environments and CI/CD pipeline operational.

- Reference/master-data plan and gateway-account dependencies confirmed.

Design

Purpose. Convert requirements into a buildable technical and experience design that enforces tenancy, security and the single-source-of-truth principle.

Key outcomes:

- Architecture baseline (schema-per-tenant, API gateway/BFF, services).

- Conceptual data model and migration approach.

- Design system (light/dark, component library, WCAG 2.1 AA tokens) and API contracts.

Development

Purpose. Build the platform in value-sequenced increments, each demoable and independently acceptable, with quality gates enforced in CI.

Key outcomes:

- M1 Essentials, M2 Sales, M3 Operations, M4 Commercial delivered.

- Cross-module workflows wired (Lead-to-Cash, Procure-to-Pay, Service, Onboarding, Employee).

- Each increment passes integration + smoke tests before promotion.

Testing / Hardening

Purpose. Prove the system against functional, non-functional, security and acceptance targets, and drive the defect backlog to the release bar.

Key outcomes:

- Security (SAST/DAST + pen-test), performance/load, tenancy isolation verified.

- System + regression suites green; UAT executed against AC-01–AC-10.

- No open Critical/High defects; release readiness signed.

Deployment

Purpose. Release to production with zero/low downtime and a tested rollback, then stabilise under heightened support.

Key outcomes:

- Rehearsed cut-over via runbook; blue-green/rolling release.

- Automated tenant provisioning verified in production.

- Hyper-care monitoring active to SLA.

Post-Launch Optimisation

Purpose. Transition to steady-state operations, tune the AI layer and reporting, and route further change through governed intake.

Key outcomes:

- Handover to AMC (Bronze/Silver/Gold) support.

- AI suggestion relevance tuned from real usage feedback.

- Enhancement and optimisation backlog managed via change control.

# 3.  Detailed Task Breakdown (Deep Workflow)

Each phase below is decomposed into epic-level task blocks. A block is sized as an epic (typically 1–3 sprints of a squad) and is intended to be imported as a parent issue, with the FR-IDs in its description expanded into child stories. Effort/Complexity uses T-shirt sizing (S/M/L/XL) plus a complexity flag; Priority reflects the dominant MoSCoW weighting of the requirements it carries.

Owner role legend EM Engagement Manager · SA Solution Architect · BA Business Analyst · TL Tech Lead · BE Backend Engineer · FE Frontend Engineer · FS Full-stack · UX UX/UI Designer · QA QA/Test Engineer · SEC Security & Compliance · DO DevOps/SRE · DA Data Engineer · PO Product Owner (client).

## Phase 0 — Discovery, Initiation & Design  (M0 — Baseline)

WF-0.1  PDD Sign-off & Baseline Lock

| Description | Walk the client through the PDD, resolve open points, and obtain countersignature so scope, FRs and acceptance criteria become the controlled baseline. Stand up the change-control register. |
| --- | --- |
| Inputs / Dependencies | Approved scope (REF-001); PDD v1.0; Section 24 sign-off; stakeholder availability. |
| Output / Deliverables | Signed PDD; locked requirements baseline; change-control log; distribution to delivery team. |
| Owner (role) | EM (A), PO (R), SA/QA (C) |
| Tools / Tech | Confluence/Notion, e-signature, Jira (baseline epic import) |
| Effort / Complexity | S — low complexity, high dependency |
| Priority | Must (gating) |

WF-0.2  Solution Design & Architecture Baseline

| Description | Produce the detailed technical design: logical tiers (presentation, API gateway/BFF, module services, data, cross-cutting), schema-per-tenant model, tenant-context propagation, AI-engine placement, and the API-first contract style. Confirm tech-stack versions. |
| --- | --- |
| Inputs / Dependencies | PDD Sec. 11–12; NFR targets; FR module catalogue; security controls (Sec. 15). |
| Output / Deliverables | Architecture baseline doc; C4/sequence views; API contract conventions (OpenAPI); ADRs; tech-stack version lock. |
| Owner (role) | SA (A/R), TL/SEC (C) |
| Tools / Tech | OpenAPI/Swagger, draw.io/Structurizr, ADR repo |
| Effort / Complexity | L — high complexity (tenancy + AI) |
| Priority | Must |

WF-0.3  Environments & DevSecOps Pipeline Setup

| Description | Provision Dev/QA/Staging/Prod on managed cloud (AWS, IaC), build the CI/CD pipeline with automated build/test/deploy and quality gates (SAST/DAST, dependency & secrets scanning), wire centralised logging/metrics/tracing. |
| --- | --- |
| Inputs / Dependencies | Architecture baseline; cloud account; IaC standards (REF-003 Secure SDLC). |
| Output / Deliverables | Four environments; CI/CD pipeline with gates; observability stack; secrets vault; branch & release strategy. |
| Owner (role) | DO (A/R), SEC/SA (C) |
| Tools / Tech | Terraform, Git pipelines, Docker, Redis, observability suite, secrets vault |
| Effort / Complexity | L — foundational, high reuse |
| Priority | Must |

WF-0.4  Conceptual Data Model & Migration Strategy

| Description | Define the shared master entities (customer, product, employee), the control-plane vs tenant-schema split, referential-integrity rules, and the reference/master-data load approach for onboarding. |
| --- | --- |
| Inputs / Dependencies | PDD Sec. 13 entity overview; client master-data sources; tenancy model. |
| Output / Deliverables | Conceptual ERD; control-plane vs tenant schema map; data-load templates; migration/runbook approach. |
| Owner (role) | DA (A/R), SA (C), PO (C) |
| Tools / Tech | PostgreSQL, ERD tooling, migration framework (versioned/reversible) |
| Effort / Complexity | M — integrity-critical |
| Priority | Must |

WF-0.5  Delivery Governance & Traceability Setup

| Description | Operationalise governance: RACI, milestone gates, risk register (R-01–R-10), the FR/NFR→task→test→AC traceability matrix, and the definition of done/ready for squads. |
| --- | --- |
| Inputs / Dependencies | PDD Sec. 6 (stakeholders/RACI), Sec. 19 (milestones), Sec. 21 (risks), Sec. 23 (AC). |
| Output / Deliverables | Live RACI; gated milestone plan; risk register; traceability matrix scaffold; DoR/DoD. |
| Owner (role) | EM (A/R), QA/BA (C) |
| Tools / Tech | Jira + traceability plugin, risk register, dashboards |
| Effort / Complexity | S–M — governance backbone |
| Priority | Must |

WF-0.6  UX/UI Design System & Accessibility Baseline

| Description | Establish the component library, light/dark theming, navigation IA across 16 modules, the AI Suggestions surface pattern, and WCAG 2.1 AA design tokens. Prototype the Executive Overview and a representative module. |
| --- | --- |
| Inputs / Dependencies | FR-PLT-006, NFR-08/09; module catalogue; brand guidance. |
| Output / Deliverables | Design system + tokens; key screen prototypes; accessibility checklist; UX acceptance heuristics. |
| Owner (role) | UX (A/R), FE/PO (C) |
| Tools / Tech | Figma, component-library framework, contrast/a11y checkers |
| Effort / Complexity | M — broad surface area |
| Priority | Should |

## Phase 1 — Foundation & Essentials  (M1 — Essentials)

WF-1.1  Identity, Authentication & MFA

| Description | Implement standards-based sign-in (OAuth 2.0/OIDC, JWT sessions) with enforced password policy, TOTP MFA, short-lived tokens, secure cookie flags, and idle/absolute session timeouts. Covers FR-PLT-002, NFR-05. |
| --- | --- |
| Inputs / Dependencies | Architecture baseline; security controls (Sec. 15.1); identity provider config. |
| Output / Deliverables | Auth service; MFA enrolment/verify flows; session policy; login/edge security tests. |
| Owner (role) | BE (R), SEC (A/C), FE (C) |
| Tools / Tech | NestJS, OAuth2/OIDC, TOTP, Redis (sessions) |
| Effort / Complexity | M — security-critical |
| Priority | Must |

WF-1.2  Multi-Tenancy & Schema Isolation

| Description | Provision schema-per-tenant isolation with a control-plane schema for tenants/plans/global config; bind tenant context at authentication and inject it into the data-access layer so every query is automatically tenant-constrained. Covers FR-PLT-001, NFR-04. |
| --- | --- |
| Inputs / Dependencies | Data model (WF-0.4); auth service (WF-1.1); provisioning approach. |
| Output / Deliverables | Tenant-context middleware; per-tenant schema provisioning primitive; isolation guards; automated tenancy tests. |
| Owner (role) | SA (A), BE (R), QA (C) |
| Tools / Tech | PostgreSQL multi-schema, NestJS interceptors, test harness |
| Effort / Complexity | XL — highest architectural risk (R-02) |
| Priority | Must |

WF-1.3  RBAC & Branch-Scoping Engine

| Description | Implement the role model and permission matrix (Sec. 8) as the intersection of role × tenant × branch, with least-privilege defaults, segregation of duties for financial approvals, and audit-logged privilege elevation. Covers FR-PLT-003, FR-ADM-003. |
| --- | --- |
| Inputs / Dependencies | RBAC matrix (Sec. 8); tenancy engine (WF-1.2); role definitions. |
| Output / Deliverables | Authorisation service; role/permission admin; branch-scope resolver; access-control test suite. |
| Owner (role) | BE (R), SEC (A/C) |
| Tools / Tech | NestJS guards/policies, PostgreSQL, policy tests |
| Effort / Complexity | L — broad cross-cutting impact |
| Priority | Must |

WF-1.4  Audit Logging & Observability Foundation

| Description | Provide an immutable, time-stamped audit log of all state-changing actions attributable to user+tenant, plus centralised logging/metrics/tracing and SLA health dashboards. Covers FR-PLT-007, NFR-07/12. |
| --- | --- |
| Inputs / Dependencies | Auth/RBAC context; observability stack (WF-0.3). |
| Output / Deliverables | Append-only audit service; audit query/review UI; health dashboards; alerting rules. |
| Owner (role) | BE (R), DO (A/C), SEC (C) |
| Tools / Tech | Append-only store, log/metric/trace pipeline, dashboards |
| Effort / Complexity | M — reused everywhere |
| Priority | Must |

WF-1.5  Executive Overview + AI Suggestions Skeleton

| Description | Build the aggregated KPI dashboard (revenue, workforce, opportunities, ticket resolution, asset uptime) scoped to user/branch, with date-range & branch filters and an AI Suggestions panel scaffold (full engine in WF-5.6). Covers FR-EXO-001/002/004/007. |
| --- | --- |
| Inputs / Dependencies | Design system (WF-0.6); RBAC scope; KPI source contracts. |
| Output / Deliverables | Executive dashboard; widget refresh cadence; filter framework; AI panel placeholder with deep-link routing. |
| Owner (role) | FS (R), UX/BA (C) |
| Tools / Tech | React+TS, charting library, BFF aggregation |
| Effort / Complexity | M — depends on later module data |
| Priority | Must |

WF-1.6  CRM Essentials — Leads, Contacts, Accounts, Import & Dedupe

| Description | Deliver the CRM master: leads with scoring/source tracking, contacts with interaction history, organisations with parent-child hierarchy and 360 view, CSV/Excel import with field mapping, and exact/fuzzy deduplication. Covers FR-CRM-001/002/003/004/010. |
| --- | --- |
| Inputs / Dependencies | Data model; RBAC; tenancy; design system. |
| Output / Deliverables | CRM master entities & UI; import wizard; Find-Duplicates tool; CRM master tests. |
| Owner (role) | FS (R), BA (C) |
| Tools / Tech | React+TS, NestJS, PostgreSQL, fuzzy-match lib |
| Effort / Complexity | L — large surface, M1 backbone |
| Priority | Must |

## Phase 2 — Finance & Sales  (M2 — Sales)

WF-2.1  Financial Core — GL, AP, AR, Expenses, Reconciliation

| Description | Build the financial backbone against a shared chart of accounts: Finance Overview, General Ledger (journals, COA, audit trails), Accounts Payable (approval queue, scheduled settlements), Accounts Receivable (invoices, receipts), Expense Management (multi-step approvals), and Bank Reconciliation with discrepancy flags. Period-close locks and ageing analysis. Covers FR-FIN-001..007/010/011. |
| --- | --- |
| Inputs / Dependencies | Data model (finance entities); RBAC (SoD for approvals); tenancy. |
| Output / Deliverables | Finance modules + UI; period-close controls; AP/AR ageing; ACID-compliant posting (NFR-06). |
| Owner (role) | BE (R), BA/SEC (C), PO (C) |
| Tools / Tech | NestJS, PostgreSQL (ACID), approval workflow engine |
| Effort / Complexity | XL — controls-heavy, audit-critical |
| Priority | Must |

WF-2.2  CRM Pipeline — Deals, Quotations, Sales Orders, Catalogue

| Description | Deliver opportunity tracking (value, win-probability, stages), product/service catalogue with pricing matrices, quotations with line items/discounts, and sales orders generated on quote acceptance. Covers FR-CRM-014/017/018/020. |
| --- | --- |
| Inputs / Dependencies | CRM Essentials (WF-1.6); catalogue data; finance posting contracts (WF-2.4). |
| Output / Deliverables | Pipeline + quoting + order modules; quote→order conversion; catalogue admin. |
| Owner (role) | FS (R), BA (C) |
| Tools / Tech | React+TS, NestJS, PostgreSQL |
| Effort / Complexity | L — core revenue path |
| Priority | Must |

WF-2.3  Multi-Currency & FX Integration

| Description | Add multi-currency across quotations, orders and invoices with live FX via Open Exchange Rates, caching, and rate-at-transaction-time recording. Covers FR-CRM-019, FR-FIN-009, FR-PLT-008, NFR-13. |
| --- | --- |
| Inputs / Dependencies | Finance + CRM transactional entities; OXR credentials; integration controls (Sec. 14). |
| Output / Deliverables | Currency service; FX cache; rate-stamped documents; FX resilience (retry/circuit-breaker). |
| Owner (role) | BE (R), SA (C) |
| Tools / Tech | Open Exchange Rates API, Redis cache, resilient HTTP client |
| Effort / Complexity | M — integration + correctness |
| Priority | Must |

WF-2.4  Cross-Module Posting — Order→Finance→Inventory

| Description | Wire the single-source-of-truth backbone of Lead-to-Cash: accepted quote auto-creates a sales order, posts a receivable to Finance, and reserves/decrements inventory — with no re-entry. Covers FR-CRM-018, FR-FIN-008, FR-SCM-007. |
| --- | --- |
| Inputs / Dependencies | Finance core (WF-2.1); pipeline (WF-2.2); inventory primitives (Phase 3 dependency for full decrement). |
| Output / Deliverables | Event/posting orchestration; idempotent cross-module transactions; integration tests proving zero re-entry (AC-02). |
| Owner (role) | SA (A), BE (R), QA (C) |
| Tools / Tech | Message queue, transactional outbox, NestJS |
| Effort / Complexity | L — integration risk hotspot |
| Priority | Must |

WF-2.5  Sales Analytics, Collaboration & Enablement

| Description | Add Actions/Tasks/Events (with Google/Outlook calendar sync), Approvals, Documents, reports (tabular/summary/matrix with scheduling), dashboards (pipeline, lead-source, heatmaps), leaderboard and personal sales dashboard. Covers FR-CRM-005..009/011/012/021/022 and calendar integration. |
| --- | --- |
| Inputs / Dependencies | CRM pipeline; reporting framework; calendar OAuth (Sec. 14). |
| Output / Deliverables | Collaboration suite; calendar sync; sales reports/dashboards; leaderboard. |
| Owner (role) | FS (R), UX (C) |
| Tools / Tech | React+TS, Google/Outlook Calendar APIs, reporting engine |
| Effort / Complexity | M — breadth over depth |
| Priority | Should |

## Phase 3 — Operations  (M3 — Operations)

WF-3.1  Supply Chain — Inventory, Vendors, Procurement, Transfers, POs

| Description | Deliver SCM Overview, central item/SKU registry with unit values, vendor directory with reliability ratings, procurement sourcing (RFP/bidding), inter-hub transfers, and purchase orders that post to Finance on receipt with auto inventory increment and low-stock alerts. Covers FR-SCM-001..008. |
| --- | --- |
| Inputs / Dependencies | Finance posting (WF-2.4); data model; RBAC. |
| Output / Deliverables | SCM module + UI; PO→goods-receipt→payable flow (Procure-to-Pay); reorder alerting. |
| Owner (role) | BE (R), BA (C) |
| Tools / Tech | NestJS, PostgreSQL, alerting |
| Effort / Complexity | L — multi-entity, finance-linked |
| Priority | Must |

WF-3.2  Asset Management — Registry, Work Orders, SOPs, Reliability

| Description | Build the asset registry with status/health indicators, preventive-maintenance and repair work orders with technician assignment, compliance SOPs/checklists/sign-offs, and reliability metrics (MTTR/MTBF) feeding the Executive uptime KPI. Covers FR-AST-001..005. |
| --- | --- |
| Inputs / Dependencies | RBAC; ticket linkage (WF-3.3); EXO KPI contract (WF-1.5). |
| Output / Deliverables | Asset module + UI; work-order workflow; MTTR/MTBF computation; uptime KPI feed. |
| Owner (role) | FS (R), BA (C) |
| Tools / Tech | React+TS, NestJS, PostgreSQL |
| Effort / Complexity | M |
| Priority | Should |

WF-3.3  Ticket Management — Service Desk, Dispatch, Field, SLA

| Description | Deliver Support Overview, service desk triage with prioritisation/routing, map-based dispatch console, field-services records, and SLA timers tracking response/resolution against tier targets with breach-risk escalation; optional CSAT on close. Covers FR-TKT-001..006. |
| --- | --- |
| Inputs / Dependencies | RBAC; asset work-order linkage; CSAT (FR-CRM-013). |
| Output / Deliverables | Ticketing module + UI; SLA engine; dispatch map; Service lifecycle (intake→dispatch→execution→closure). |
| Owner (role) | FS (R), BE/UX (C) |
| Tools / Tech | React+TS, NestJS, mapping SDK, SLA timer service |
| Effort / Complexity | L — SLA + dispatch complexity |
| Priority | Must |

WF-3.4  Procure-to-Pay & Service Lifecycle Integration

| Description | Prove the end-to-end operational workflows across modules: Procure-to-Pay (sourcing→PO→receipt→payable→settlement→reconciliation) and Service & Ticket lifecycle (intake→dispatch→field/work-order→SLA→closure→CSAT). Covers PDD Sec. 9.2 and 9.3. |
| --- | --- |
| Inputs / Dependencies | WF-3.1/3.2/3.3; Finance AP (WF-2.1); audit log. |
| Output / Deliverables | Wired cross-module workflows; integration test scenarios; reconciliation checks. |
| Owner (role) | SA (A), QA (R), BE (C) |
| Tools / Tech | Integration test framework, message queue |
| Effort / Complexity | M — validation-heavy |
| Priority | Must |

## Phase 4 — Human Capital & Administration

WF-4.1  Human Capital — Employees, Recruiting, Onboarding, Payroll, Benefits, Time, Compliance, Vault

| Description | Build HCM: org chart/employee records, recruiting (List/Kanban stages), onboarding milestones (hardware/system/credentials), payroll (salary, dynamic tax, withholdings, paystubs), benefits (incl. 401(k) calculator), time tracking (attendance, geofencing), compliance (certifications, SOC-2-aligned audit logs) and a secure document vault. Covers FR-HCM-001..008. |
| --- | --- |
| Inputs / Dependencies | RBAC (HR scope); audit log; data model; identity provisioning. |
| Output / Deliverables | HCM modules + UI; payroll engine; onboarding workflow; compliance tracking; vault. |
| Owner (role) | BE (R), BA/SEC (C) |
| Tools / Tech | NestJS, PostgreSQL, object storage (vault), tax-rule engine |
| Effort / Complexity | XL — payroll + compliance depth |
| Priority | Must |

WF-4.2  Administration & System Settings

| Description | Deliver Workspace & Billing administration (sub-tenant orgs, tiers, admin accounts), System Settings (preferences, light/dark themes, theme modifiers, security controls), user/role/permission administration, and an admin configuration audit trail. Covers FR-ADM-001..004. |
| --- | --- |
| Inputs / Dependencies | RBAC engine; tenancy; audit log; theming from design system. |
| Output / Deliverables | Admin console; settings; user/role management UI; config audit trail. |
| Owner (role) | FS (R), SEC (C) |
| Tools / Tech | React+TS, NestJS |
| Effort / Complexity | M |
| Priority | Must |

WF-4.3  Employee Lifecycle Integration

| Description | Wire the people workflow: recruiting→onboarding→least-privilege account/role provisioning→time/benefits/compliance→payroll. Covers PDD Sec. 9.5, linking HCM to identity/RBAC (FR-PLT-003, FR-ADM-003). |
| --- | --- |
| Inputs / Dependencies | WF-4.1; WF-1.1/1.3; admin console. |
| Output / Deliverables | Integrated lifecycle; provisioning automation; lifecycle test scenarios. |
| Owner (role) | SA (A), BE (R), QA (C) |
| Tools / Tech | Workflow orchestration, identity APIs |
| Effort / Complexity | M |
| Priority | Should |

## Phase 5 — Multi-Branch & Commercialisation  (M4 — Commercial)

WF-5.1  Multi-Branch Management & Group Executive Dashboard

| Description | Deliver branch directory (unlimited branches, address/contact/hours/per-location currency), per-branch P&L (revenue, COGS, opex, net profit; PDF/CSV export), staff assignment/transfer with branch-scoped access, per-branch inventory with inter-branch transfers and scoped alerts, sales-by-branch segmentation, and the Group Executive Dashboard aggregating KPIs across branches. Covers FR-BRN-001..006. |
| --- | --- |
| Inputs / Dependencies | RBAC branch scope (WF-1.3); Finance/CRM/SCM data; reporting engine. |
| Output / Deliverables | Multi-branch module; branch P&L + exports; Group Executive Dashboard; consolidated views. |
| Owner (role) | BE (R), SA/BA (C), PO (C) |
| Tools / Tech | NestJS, PostgreSQL, reporting/export engine |
| Effort / Complexity | L — consolidation correctness (AC-04) |
| Priority | Must |

WF-5.2  Subscription & Tier Management

| Description | Implement four tiers (Starter/Growth/Business/Enterprise) with feature gating (SLA, support response, dedicated resources), automated seat counting with limit alerts, upgrade/downgrade workflows (immediate or next cycle), and the annual pre-pay 10% discount. Covers FR-SUB-001..005. |
| --- | --- |
| Inputs / Dependencies | Admin/billing scaffolding (WF-4.2); tenancy; pricing config. |
| Output / Deliverables | Tier engine; seat metering + alerts; plan-change workflows. |
| Owner (role) | BE (R), PO (C) |
| Tools / Tech | NestJS, PostgreSQL, scheduler |
| Effort / Complexity | M |
| Priority | Must |

WF-5.3  Billing & Invoicing Engine

| Description | Generate and deliver monthly invoices automatically, provide an invoice-history portal with PDF download, compute proration for mid-cycle changes, and run failed-payment retry/dunning with grace-period notifications before suspension. Covers FR-SUB-006..009. |
| --- | --- |
| Inputs / Dependencies | Tier engine (WF-5.2); email/SMTP integration; payment status from gateways. |
| Output / Deliverables | Invoicing engine; PDF invoices + portal; proration; dunning/retry workflow. |
| Owner (role) | BE (R), SEC (C) |
| Tools / Tech | NestJS, PDF generation, scheduler, SMTP |
| Effort / Complexity | L — billing edge cases |
| Priority | Must |

WF-5.4  Payment Gateways & Automated Provisioning

| Description | Integrate Stripe (cards, Apple/Google Pay, 135+ currencies, tax), PayPal (wallet/credit/global) and Razorpay (UPI/NEFT/IMPS/cards/EMI) with per-tenant gateway selection and scoped credentials; trigger automated cloud workspace provisioning (isolated schema) on activation. Idempotency keys throughout. Covers FR-SUB-010..015. |
| --- | --- |
| Inputs / Dependencies | Tenancy provisioning primitive (WF-1.2); billing engine; secrets vault; merchant accounts (client dependency). |
| Output / Deliverables | Three gateway integrations; per-tenant gateway config; automated provisioning; idempotent payment ops. |
| Owner (role) | BE (R), SEC/DO (C) |
| Tools / Tech | Stripe/PayPal/Razorpay SDKs, secrets vault, idempotency keys |
| Effort / Complexity | XL — external + financial risk (R-03) |
| Priority | Must |

WF-5.5  Public SaaS Landing Page

| Description | Build the standalone, framework-free, CDN-ready dark-premium marketing site: hero with key stats and dual CTAs, fixed blur-backdrop nav, 16-module showcase grid (colour-coded), features bento grid, 4-step 'How It Works' timeline, and a pricing section with all four tiers and CTAs. Covers FR-LP-001..007. |
| --- | --- |
| Inputs / Dependencies | Design system; pricing/tier data; module catalogue copy structure. |
| Output / Deliverables | Production landing page (HTML/CSS/JS); sign-up entry to onboarding flow. |
| Owner (role) | FE (R), UX (C) |
| Tools / Tech | HTML/CSS/JS, CDN hosting |
| Effort / Complexity | M — standalone artefact |
| Priority | Should |

WF-5.6  AI Suggestions Engine (Full)

| Description | Complete the cross-module recommendation engine: ingest financial/sales/service/asset/HR signals within the tenant boundary, compute a business-impact score, produce ranked plain-language recommendations with deep links, refresh on a recurring interval (~15 min), respect user data scope, and support dismiss/snooze/pin persisted per user. Covers FR-EXO-003/005/006 and PDD Sec. 11.4. |
| --- | --- |
| Inputs / Dependencies | Module data across Phases 1–5; EXO panel (WF-1.5); RBAC scope. |
| Output / Deliverables | AI engine service (rules + ML scoring); ranking + deep-link; per-user state; scoped caching. |
| Owner (role) | BE/DA (R), SA (C) |
| Tools / Tech | Recommendation service (rules+ML), Redis cache, scheduler |
| Effort / Complexity | L — relevance tuning risk (R-07) |
| Priority | Must |

## Phase 6 — Hardening & UAT  (gates M5)

WF-6.1  Security Testing & Penetration Test

| Description | Run SAST/DAST, dependency and secrets scanning, access-control and tenancy-isolation testing, and an external penetration test; remediate findings. Verifies NFR-05, AC-03/07 and de-risks R-02. |
| --- | --- |
| Inputs / Dependencies | All built modules; tenancy/RBAC; CI security gates. |
| Output / Deliverables | Security test reports; pen-test report + remediation; tenancy-isolation evidence. |
| Owner (role) | SEC (A/R), QA/BE (C) |
| Tools / Tech | SAST/DAST, dependency scanners, pen-test tooling |
| Effort / Complexity | L — release-blocking |
| Priority | Critical |

WF-6.2  Performance & Load Testing

| Description | Load/stress test against NFR-02/03 (page < 2 s p95, API < 500 ms, horizontal scalability); profile and tune caching, queries and hot paths. De-risks R-05. |
| --- | --- |
| Inputs / Dependencies | Production-like Staging; representative data volumes. |
| Output / Deliverables | Performance test report; tuning changes; scalability evidence. |
| Owner (role) | QA/DO (R), SA (C) |
| Tools / Tech | Load-testing tools, profilers, Redis |
| Effort / Complexity | M |
| Priority | Must |

WF-6.3  System & Regression Test Execution

| Description | Execute scripted end-to-end scenarios for all five workflows (Sec. 9) and run the automated regression suite; confirm zero re-entry across modules. Verifies AC-01/02. |
| --- | --- |
| Inputs / Dependencies | Test scenarios; traceability matrix; built modules. |
| Output / Deliverables | System/regression results; updated traceability; defect tickets. |
| Owner (role) | QA (A/R), BA (C) |
| Tools / Tech | Test automation framework, Jira |
| Effort / Complexity | M |
| Priority | Must |

WF-6.4  UAT Cycle Management

| Description | Run client-led UAT against AC-01–AC-10 using guided scenarios; manage entry/exit quality gates; capture acceptance per milestone. De-risks R-10. |
| --- | --- |
| Inputs / Dependencies | UAT environment; participant availability (client dependency); acceptance criteria. |
| Output / Deliverables | UAT execution log; acceptance records; deferral agreements for non-blocking items. |
| Owner (role) | PO (A), EM/QA (R), BA (C) |
| Tools / Tech | UAT tracker, Staging environment |
| Effort / Complexity | M — dependency-sensitive |
| Priority | Must |

WF-6.5  Defect Triage & Release Readiness

| Description | Triage by severity (Critical/High/Medium/Low), drive to the exit bar (no open Critical/High), and confirm release readiness: security passed, performance met, runbook + rollback verified. Verifies AC-09, Sec. 17.2. |
| --- | --- |
| Inputs / Dependencies | Defect register; test reports; runbook. |
| Output / Deliverables | Closed Critical/High defects; signed release-readiness checklist. |
| Owner (role) | QA (A/R), EM/DO (C) |
| Tools / Tech | Jira, dashboards |
| Effort / Complexity | M |
| Priority | Must |

## Phase 7 — Go-Live & Hyper-Care  (M5 — Go-Live)

WF-7.1  Production Cut-over & Runbook Execution

| Description | Execute the rehearsed cut-over runbook using blue-green/rolling release with versioned, reversible DB migrations applied in Staging first; verify automated tenant provisioning in production; health checks gate the release with automatic abort on failure. Verifies AC-10. |
| --- | --- |
| Inputs / Dependencies | Release-readiness sign-off; runbook; reference/master data load. |
| Output / Deliverables | Live production service; provisioning verified; rollback path proven. |
| Owner (role) | DO (A/R), SA/EM (C) |
| Tools / Tech | CI/CD, IaC, migration framework |
| Effort / Complexity | M — high-stakes window |
| Priority | Critical |

WF-7.2  Hyper-Care & Monitoring

| Description | Provide a heightened-monitoring, rapid-response period immediately post go-live; track SLA dashboards, triage incidents fast, and stabilise before transition to standard support. |
| --- | --- |
| Inputs / Dependencies | Live system; observability; on-call rota. |
| Output / Deliverables | Hyper-care log; incident resolutions; stabilisation report; SLA evidence. |
| Owner (role) | DO/EM (R), SEC (C) |
| Tools / Tech | Observability suite, alerting, on-call |
| Effort / Complexity | M |
| Priority | Must |

WF-7.3  Handover to AMC Support

| Description | Transition to the Annual Maintenance Contract (Bronze/Silver/Gold), hand over runbooks/architecture/knowledge, and stand up the corrective/adaptive/preventive/perfective maintenance model and enhancement intake via change control. Covers PDD Sec. 22. |
| --- | --- |
| Inputs / Dependencies | Stabilised production; documentation; support tier selection. |
| Output / Deliverables | Signed handover; support runbooks; AMC operating model; enhancement backlog. |
| Owner (role) | EM (A/R), DO/SA (C) |
| Tools / Tech | Knowledge base, ticketing, runbooks |
| Effort / Complexity | S–M |
| Priority | Should |

# 4.  Workflow Dependencies & Sequencing

Sequencing follows the value-and-risk logic of the PDD: foundation first (no module is correct without tenancy, RBAC and audit), then revenue path, then operations, then people/admin, then commercialisation, then hardening and release. The table records the principal epic-level dependencies.

## 4.1  Dependency Register (predecessor → successor)

| Task | Depends on (must finish/started) | Enables / blocks |
| --- | --- | --- |
| WF-1.1 Auth/MFA | WF-0.2 Architecture, WF-0.3 Pipeline | All authenticated features; WF-1.2/1.3 |
| WF-1.2 Multi-tenancy | WF-0.4 Data model, WF-1.1 | Every module's data isolation; WF-5.4 provisioning |
| WF-1.3 RBAC/branch scope | WF-1.2 | All module access; WF-5.1 branch P&L |
| WF-1.4 Audit/observability | WF-0.3, WF-1.1 | Compliance (NFR-07); WF-6.1 security evidence |
| WF-1.6 CRM Essentials | WF-1.2, WF-1.3, WF-0.6 | WF-2.2 pipeline |
| WF-2.1 Financial core | WF-1.2/1.3 | WF-2.4 posting; WF-5.1 branch P&L; WF-5.3 billing GL |
| WF-2.2 CRM pipeline | WF-1.6 | WF-2.4; Lead-to-Cash |
| WF-2.4 Cross-module posting | WF-2.1, WF-2.2, (WF-3.1 for full inventory) | AC-02 zero re-entry; Lead-to-Cash, Procure-to-Pay |
| WF-3.1 Supply Chain | WF-2.1 (finance posting) | WF-2.4 full inventory decrement; WF-3.4 |
| WF-3.3 Ticket/SLA | WF-1.3 | WF-3.2 work-order link; Service lifecycle |
| WF-4.1 HCM | WF-1.2/1.3, WF-1.4 | WF-4.3 lifecycle; EXO workforce KPI |
| WF-5.1 Multi-branch | WF-1.3, WF-2.1, WF-2.2, WF-3.1 | AC-04 consolidation; Group dashboard |
| WF-5.4 Gateways & provisioning | WF-1.2, WF-5.3 | AC-05 billing; subscriber onboarding |
| WF-5.6 AI engine (full) | Module data from Phases 1–5, WF-1.5 | AC-06; EXO suggestions |
| WF-6.x Hardening/UAT | All build epics (Phases 1–5) | M5 gate; WF-7.1 go-live |
| WF-7.1 Cut-over | WF-6.5 readiness | M5 — Go-Live; WF-7.2 hyper-care |

## 4.2  Parallel vs Sequential

- Strictly sequential spine — WF-0.2 → WF-1.1 → WF-1.2 → WF-1.3 → WF-1.4. This foundation must be stable before any module is built; attempting modules first creates rework and tenancy-isolation risk.

- Parallelisable within a phase — once foundation is set, module squads run in parallel: e.g., in Phase 2, Finance (WF-2.1) and CRM pipeline (WF-2.2) proceed concurrently and converge at WF-2.4; in Phase 3, SCM/AST/TKT run as parallel squads.

- Cross-phase parallelism — the Landing Page (WF-5.5) and UX system work can begin early and in parallel; the AI engine (WF-5.6) is built last because it consumes data from all prior modules.

- Continuous activities — audit logging, observability, security gates, and regression automation run across every phase rather than as a single late task.

## 4.3  Critical Path

The critical path runs through the tenancy/finance/commercialisation spine, because these carry the highest integration and external-dependency risk and gate the most acceptance criteria:

Critical path WF-0.2 Architecture → WF-1.2 Multi-tenancy → WF-1.3 RBAC → WF-2.1 Finance core → WF-2.4 Cross-module posting → WF-3.1 Supply Chain → WF-5.1 Multi-branch → WF-5.4 Gateways & provisioning → WF-6.1–6.5 Hardening/UAT → WF-7.1 Cut-over. Watch items on the path: WF-1.2 (architectural risk R-02), WF-2.4 (integration integrity, AC-02), and WF-5.4 (external gateways + merchant-account client dependency, R-03/R-04). Slippage in any of these moves the M5 go-live date one-for-one.

# 5.  Roles & Responsibilities (RACI Model)

R Responsible (does the work)  ·  A Accountable (owns the outcome, one per row)  ·  C Consulted (two-way input)  ·  I Informed (kept up to date).

## 5.1  Delivery Roles

| Role | Remit |
| --- | --- |
| Engagement Manager (EM) | Overall delivery accountability, schedule, commercials, governance and escalation. |
| Product Owner (PO, client) | Requirements authority, prioritisation, UAT and acceptance sign-off. |
| Solution Architect (SA) | Technical design authority, architectural integrity, integration design. |
| Tech Lead (TL) | Squad-level technical leadership, code quality, sprint execution. |
| Backend / Full-stack Eng (BE/FS) | Services, business logic, integrations, data access. |
| Frontend Eng / UX (FE/UX) | Web UI, design system, accessibility, landing page. |
| QA / Test Lead (QA) | Test strategy, automation, quality gates, defect governance. |
| Security & Compliance (SEC) | Security controls, tenancy isolation, data protection, compliance posture. |
| DevOps / SRE (DO) | CI/CD, environments, provisioning, observability, reliability, cut-over. |
| Data Engineer (DA) | Data model, migrations, master-data loads, AI signal pipelines. |
| Business Analyst (BA) | Requirements elicitation, traceability, UAT support. |

## 5.2  Phase RACI Matrix

| Activity / phase | EM | PO | SA | QA | SEC | DO | Squads |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Baseline & governance (P0) | A | R | C | C | C | C | I |
| Architecture & design (P0) | I | C | A | C | C | C | R |
| Foundation build (P1) | A | I | C | C | C | R | R |
| Module build (P2–P4) | A | C | C | C | I | I | R |
| Commercialisation (P5) | A | C | C | C | C | R | R |
| Security & compliance | I | I | C | C | A/R | C | C |
| Testing & hardening (P6) | A | C | C | R | C | C | C |
| UAT & acceptance (P6) | C | A | I | R | I | I | C |
| Go-live & cut-over (P7) | A | C | C | C | C | R | C |
| Hyper-care & handover (P7) | A | I | C | C | C | R | C |

Note. The PDD's contractual RACI (Sec. 6.2) governs the formal client-facing gates; the matrix above extends it to the operational delivery activities. Where the two overlap (requirements sign-off, UAT, go-live approval), the Sponsor remains the ultimate approver and the Product Owner the responsible authority.

# 6.  Risk & Bottleneck Analysis

## 6.1  Risk Register (carried & extended)

| ID | Risk | Likely. | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | Scope creep beyond the approved baseline. | Med | High | Formal change control; traceable requirements; baseline sign-off (WF-0.1/0.5). |
| R-02 | Multi-tenancy isolation defect exposing cross-tenant data. | Low | High | Schema isolation, automated tenancy tests (WF-1.2), security review + pen-test (WF-6.1). |
| R-03 | Payment-gateway integration delays/failures. | Med | High | Early sandbox work, idempotency keys, resilient clients, fallbacks (WF-5.4). |
| R-04 | Client-side dependency delays (data, sign-offs, merchant accounts). | Med | Med | Dependency tracking, early requests, schedule buffers; surfaced as KPI. |
| R-05 | Performance below NFR targets under load. | Low | Med | Performance testing, caching, horizontal scaling, profiling (WF-6.2). |
| R-06 | Data-protection/compliance gap in a tenant jurisdiction. | Low | High | Per-tenant configurable controls; GDPR/DPDP/CCPA alignment; legal review. |
| R-07 | AI suggestions perceived as low value/noisy. | Med | Low | Impact-ranking, snooze/pin, iterative tuning with feedback (WF-5.6). |
| R-08 | Key-person dependency in the delivery team. | Low | Med | Documentation, cross-skilling, knowledge sharing. |
| R-09 | Third-party outage (FX, calendar, email). | Low | Med | Circuit breakers, caching, graceful degradation, retries (WF-2.3). |
| R-10 | Inadequate UAT coverage → post-go-live defects. | Med | Med | Scripted UAT, quality gates, hyper-care, regression automation (WF-6.3/6.4). |

## 6.2  Bottleneck Analysis

Beyond discrete risks, four structural bottlenecks can throttle the whole flow if not actively managed:

| Bottleneck | Why it constrains | How to relieve |
| --- | --- | --- |
| Foundation gate (WF-1.2/1.3) | Every module squad is blocked until tenancy + RBAC are stable; it is on the critical path and parallelism collapses around it. | Staff foundation with the strongest engineers; build a tenancy test harness first; freeze the contract early so squads can mock against it. |
| Cross-module posting (WF-2.4) | Integration integrity (zero re-entry, AC-02) is where most defects concentrate; finance correctness blocks branch P&L and billing. | Transactional outbox + idempotency; contract tests between modules; reconcile against seeded test data continuously. |
| External gateways & merchant accounts (WF-5.4) | Three external integrations plus a client-supplied dependency (merchant accounts) sit late on the critical path. | Start gateway sandbox integration in Phase 0/1; track merchant-account procurement as a client dependency from day one (R-04). |
| UAT participant availability (WF-6.4) | UAT cannot start without client testers; the M5 gate depends on it. | Schedule UAT windows at baseline; pre-train participants; provide scripted scenarios to compress execution. |

Highest-attention items WF-1.2 Multi-tenancy isolation — XL effort, R-02 (high impact), on the critical path. Treat as a spike-then-build with an explicit isolation test gate before any module begins. WF-5.4 Gateways & provisioning — XL effort, R-03/R-04, financial blast radius. De-risk early with sandbox integrations and idempotency from the first commit.

# 7.  Automation & Optimisation Opportunities

SAIGEN is unusually automation-friendly because integration is intrinsic to the design. The opportunities below remove manual effort, reduce error, and shorten the data-to-action cycle.

| Manual / repetitive task | Automation | Tooling / approach |
| --- | --- | --- |
| Tenant workspace setup on sign-up | Event-driven provisioning of an isolated schema + seed config on subscription activation. | Provisioning service (WF-5.4) + IaC; idempotency keys (FR-SUB-014). |
| Monthly invoice creation & delivery | Scheduled invoice generation, PDF render and email dispatch; proration computed automatically. | Billing engine (WF-5.3) + scheduler + SMTP (FR-SUB-006/008). |
| Failed-payment chasing | Automated retry/dunning with grace-period notices before suspension. | Dunning workflow + gateway webhooks (FR-SUB-009). |
| Seat counting & tier-limit policing | Continuous seat metering with threshold alerts to admins. | Metering service (WF-5.2, FR-SUB-003). |
| Re-keying between modules | Cross-module posting (order→finance→inventory) so master data is entered once. | Transactional outbox + message queue (WF-2.4, FR-PLT-005). |
| FX rate lookups | Cached live FX with rate-at-transaction stamping. | Open Exchange Rates + Redis (WF-2.3). |
| Executive insight hunting | AI engine surfaces impact-ranked, deep-linked recommendations on a 15-min refresh. | Recommendation service (WF-5.6, FR-EXO-003/005). |
| Regression & release checks | Automated unit/integration/regression suites and security gates in CI before each promotion. | CI/CD quality gates (WF-0.3, Sec. 17). |
| Tenant provisioning & migrations | Versioned, reversible DB migrations applied automatically, Staging-first. | Migration framework + blue-green release (WF-7.1). |
| Low-stock & SLA breach watching | Threshold alerts for reorder points and SLA breach-risk escalation. | Alerting rules (FR-SCM-008, FR-TKT-005). |

## 7.1  Process Improvements

- Contract-first parallelism — freeze API contracts at design so squads build and test against mocks, maximising parallel throughput and shrinking the foundation bottleneck.

- Shift-left security & tenancy — run SAST/DAST, dependency and tenancy-isolation tests in CI from Phase 1, not just in Phase 6, so isolation defects surface early (R-02).

- Traceability as a living gate — auto-link FR→task→test→AC so coverage gaps are visible per sprint rather than discovered at UAT.

- Reusable cross-cutting library — package tenant-context, RBAC guards, audit logging and resilient-integration clients once and consume everywhere, reducing per-module effort and drift.

- Feedback-driven AI tuning — use snooze/pin/dismiss telemetry to tune impact ranking continuously post-launch (mitigates R-07).

# 8.  Timeline & Milestones

Indicative durations are working-week estimates from kick-off, confirmed at detailed planning. Phases may overlap where dependencies allow. The cumulative columns assume modest overlap between adjacent module phases.

## 8.1  Phase Timeline

| Phase | Focus | Duration | Cumulative | Gate |
| --- | --- | --- | --- | --- |
| Phase 0 | Initiation & design | 2–3 wks | ~3 wks | M0 — Baseline |
| Phase 1 | Foundation & Essentials | 4–6 wks | ~7–9 wks | M1 — Essentials |
| Phase 2 | Finance & Sales | 5–7 wks | ~12–15 wks | M2 — Sales |
| Phase 3 | Operations | 5–7 wks | ~17–21 wks | M3 — Operations |
| Phase 4 | Human Capital & Admin | 3–5 wks | ~20–25 wks | (rolls to M4) |
| Phase 5 | Multi-Branch & Commercial | 4–6 wks | ~24–30 wks | M4 — Commercial |
| Phase 6 | Hardening & UAT | 3–4 wks | ~27–33 wks | gates M5 |
| Phase 7 | Go-Live & Hyper-Care | 2–3 wks | ~29–36 wks | M5 — Go-Live |

Indicative overall delivery window: approximately 29–36 working weeks (~7–8 months) from kick-off, subject to client-dependency timeliness (R-04) and final capacity planning.

## 8.2  Milestone Gates & Checkpoints

| Milestone | Definition | Gate / checkpoint |
| --- | --- | --- |
| M0 — Baseline | PDD signed; design and environments ready. | Client sign-off; pipeline + environments demo. |
| M1 — Essentials | Foundation, tenancy, dashboard and CRM Essentials demoable. | Demo acceptance; tenancy-isolation evidence. |
| M2 — Sales | Finance and full Sales operational end-to-end. | Lead-to-Cash workflow acceptance. |
| M3 — Operations | Supply, Assets and Service operational. | Procure-to-Pay & Service workflow acceptance. |
| M4 — Commercial | Multi-Branch and Subscription/Billing live. | Branch consolidation + billing (sandbox) acceptance. |
| M5 — Go-Live | UAT passed; production live; hyper-care started. | Final acceptance (AC-01–AC-10); cut-over runbook rehearsed. |

Schedule dependencies (from PDD Sec. 19) Timely client sign-off, reference/master-data provision, gateway merchant accounts, and UAT-participant availability are prerequisites. Slippage in any client dependency shifts dependent milestones one-for-one.

# 9.  Deliverables Checklist

A complete, validate-and-handoff checklist. Each item maps to one or more workflow tasks and acceptance criteria; mark complete only when the linked test/acceptance evidence exists.

## 9.1  Governance & Design

- Signed PDD baseline  + change-control register active (WF-0.1).

- Architecture baseline & ADRs  schema-per-tenant, BFF, API contracts (WF-0.2).

- Environments + CI/CD pipeline  Dev/QA/Staging/Prod with quality gates (WF-0.3).

- Conceptual data model + migration plan  master-data load templates (WF-0.4).

- RACI, risk register, traceability matrix  DoR/DoD (WF-0.5).

- Design system + accessibility baseline  WCAG 2.1 AA tokens, key prototypes (WF-0.6).

## 9.2  Platform Foundation

- Authentication + MFA  session policy (WF-1.1, FR-PLT-002).

- Multi-tenancy + schema isolation  tenancy test evidence (WF-1.2, AC-03).

- RBAC + branch scoping engine  permission matrix enforced (WF-1.3).

- Audit log + observability  health/SLA dashboards (WF-1.4, NFR-07/12).

## 9.3  Core Modules

- Executive Overview + AI panel  (WF-1.5, FR-EXO).

- CRM & Sales  Essentials + pipeline + multi-currency (WF-1.6/2.2/2.3).

- Financial Systems  GL/AP/AR/expenses/reconciliation (WF-2.1).

- Cross-module posting  zero re-entry proven (WF-2.4, AC-02).

- Supply Chain  inventory/procurement/transfers/POs (WF-3.1).

- Asset Management  registry/work orders/SOPs/reliability (WF-3.2).

- Ticket Management  service desk/dispatch/field/SLA (WF-3.3).

- Human Capital  employees/payroll/benefits/time/compliance/vault (WF-4.1).

- Administration & System Settings  (WF-4.2).

## 9.4  Commercial Platform

- Multi-Branch + Group Executive Dashboard  per-branch P&L (WF-5.1, AC-04).

- Subscription & tier management  metering + plan changes (WF-5.2).

- Billing & invoicing engine  invoices/proration/dunning (WF-5.3).

- Payment gateways + provisioning  Stripe/PayPal/Razorpay (WF-5.4, AC-05).

- Public SaaS landing page  (WF-5.5, FR-LP).

- AI Suggestions engine  ranked, deep-linked, scoped (WF-5.6, AC-06).

## 9.5  Quality, Release & Handover

- Security + pen-test reports  remediation closed (WF-6.1, AC-07).

- Performance/load test report  NFR-02/03 met (WF-6.2).

- System + regression results  traceability complete (WF-6.3, AC-01).

- UAT acceptance records  AC-01–AC-10 (WF-6.4).

- Release-readiness sign-off  no open Critical/High (WF-6.5, AC-09).

- Deployment + rollback + backup/restore evidence  (WF-7.1, AC-10).

- Hyper-care report  stabilisation to SLA (WF-7.2).

- AMC handover pack  runbooks + support model (WF-7.3).

# Appendix A — FR Coverage Map

Confirms every PDD functional-requirement group is owned by a workflow task, preserving end-to-end traceability.

| Module | FR range | Owning workflow task(s) |
| --- | --- | --- |
| EXO | FR-EXO-001..008 | WF-1.5, WF-5.6 |
| FIN | FR-FIN-001..011 | WF-2.1, WF-2.3, WF-2.4 |
| CRM | FR-CRM-001..024 | WF-1.6, WF-2.2, WF-2.3, WF-2.5 |
| SCM | FR-SCM-001..008 | WF-3.1, WF-2.4, WF-3.4 |
| AST | FR-AST-001..005 | WF-3.2 |
| TKT | FR-TKT-001..006 | WF-3.3, WF-3.4 |
| HCM | FR-HCM-001..008 | WF-4.1, WF-4.3 |
| ADM | FR-ADM-001..004 | WF-4.2, WF-1.3 |
| BRN | FR-BRN-001..006 | WF-5.1 |
| SUB | FR-SUB-001..015 | WF-5.2, WF-5.3, WF-5.4 |
| LP | FR-LP-001..007 | WF-5.5 |
| PLT | FR-PLT-001..008 | WF-1.1, WF-1.2, WF-1.3, WF-1.4, WF-2.4, WF-2.3 |

End of Workflow System  ·  derived from SAIGEN PDD v1.0  ·  EiBS — Elysian Intelligence Business Solutions