ELYSIAN INTELLIGENCE BUSINESS SOLUTIONS

EiBS Global  ·  Technology that Elevates

DREAMZONE

Institute Management System

AGILE SPRINT EXECUTION PLAN

Sprint Roadmap  ·  Epic Breakdown  ·  Team Structure  ·  Risk Register

| Prepared for | Dreamzone, Madurai |
| --- | --- |
| Prepared by | Elysian Intelligence Business Solutions (EiBS Global) |
| Document type | Agile Sprint Execution Plan |
| Source PDD reference | EIBS-DZ-IMS-2025-001 |
| Plan version | v1.0 |
| Date | 21 April 2026 |
| Planning horizon | 10 two-week sprints (~20 weeks) |
| Total scope | 10 web modules + 2 Android mobile applications |

# 1. Project Overview

The Dreamzone Institute Management System (IMS) is a custom-built, cloud-hosted, multi-tenant SaaS platform engineered exclusively for Dreamzone — a multi-branch training and placement institution headquartered in Madurai, Tamil Nadu. The platform replaces the institute's current ecosystem of paper registers, disconnected spreadsheets, and manual workflows with a single unified system where every functional module shares a live relational database.

The delivery comprises twelve shippable artefacts: ten integrated web modules accessed through a role-aware browser-based application, plus two dedicated Android mobile applications — one for staff and one for students — that provide on-the-go access to the subset of workflows relevant to each audience. All twelve artefacts are underpinned by a shared Laravel REST API, a single MySQL database, and a common authentication and authorisation layer.

### 1.1 Primary Business Goals

- Digitise the full student lifecycle — from first marketing enquiry, through counselling and enrolment, into batch delivery, fee collection, certification, and eventual placement and alumni tracking.

- Establish a single source of truth — replace fragmented Excel workbooks and paper registers with one database where student, fee, attendance, batch, and placement records are always consistent.

- Enable self-service for students and staff — through Android applications that deliver personal information, attendance, schedules, fees, and notifications directly to the mobile device.

- Centralise multi-branch operations — give head office real-time consolidated visibility while preserving branch-level data isolation for day-to-day operations.

- Automate routine administrative tasks — fee receipts, overdue reminders, payroll calculation, attendance summaries, low-stock alerts, and approval workflows.

- Provide actionable analytics — role-sensitive dashboards covering leads, admissions, revenue, attendance, HR, and placement outcomes.

### 1.2 Target User Personas

| # | Persona | Primary Interface | Key Workflows |
| --- | --- | --- | --- |
| 1 | Super Admin | Web | Global configuration, branch setup, role matrix, audit log review, consolidated analytics |
| 2 | Branch Admin | Web | Branch-scoped oversight of students, batches, staff, fees, inventory, and placements |
| 3 | Sales / Counsellor | Web + Staff App | Lead capture, pipeline management, follow-up calls, lead-to-student conversion |
| 4 | Trainer | Staff Mobile App | View schedule, mark attendance, log queries, receive task notifications |
| 5 | HR Manager | Web | Staff directory, attendance, leave, payroll runs, KRA/KPI appraisals |
| 6 | Finance Officer | Web | Fee collection, receipt issuance, expense approvals, financial reports |
| 7 | Placement Officer | Web | Interview events, placed-student tracking, alumni management |
| 8 | Student | Student Mobile App | View sessions, attendance, fees, materials, placement updates, submit feedback |

### 1.3 Success Criteria (Definition of Done for the Product)

- All 10 web modules and 2 mobile apps deployed to production, signed off against acceptance criteria, and operated by live users for at least one full billing cycle.

- Functional coverage of every requirement in PDD sections 2.1 through 2.10, traced one-to-one to delivered user stories.

- 99.9% availability SLA demonstrated across a rolling 30-day observation window post-go-live.

- Automated daily backups verified by successful restore drill; point-in-time recovery documented and tested.

- Complete source code, database schema, CI/CD pipelines, and infrastructure-as-code handed over to Dreamzone with no vendor lock-in.

- Administrative and end-user training completed; user manuals and admin runbooks delivered.

# 2. High-Level Architecture Considerations

The architecture is a classic three-tier SaaS topology extended with a mobile edge and an asynchronous notification fabric. The following considerations drive all downstream sprint planning and technical decisions.

### 2.1 Confirmed Technology Stack (per PDD Section 3)

| Layer | Technology | Role in System | Key Sprint Implications |
| --- | --- | --- | --- |
| Frontend (Web) | React.js + TypeScript | Responsive single-page application with role-aware routing, served to all admin and office users | Component library and design system must be stood up in Sprint 1 before any feature work begins |
| Backend API | Laravel (PHP) | RESTful API gateway; JWT authentication; business logic, validation, authorization | Sanctum or tymon/jwt-auth for JWT; repository pattern recommended to isolate the multi-tenant branch scope |
| Database | MySQL 8.x | ACID-compliant relational store; multi-tenant via branch_id scoping on every domain table | Row-level branch isolation enforced via Laravel global scopes; migration strategy versioned from day one |
| Mobile | Flutter (Dart) | Single codebase compiled to native Android; two apps (Student + Staff) share domain models | Shared internal Flutter package for auth, networking, and models; per-app flavour for theming and feature flags |
| Cloud / Hosting | AWS (EC2 + RDS + S3) — GCP alternative per PDD | Auto-scaling compute, managed MySQL, S3 for documents and materials, CloudFront CDN for static assets | Infrastructure-as-code (Terraform) and staged environments (dev / staging / prod) set up in Sprint 0 |
| Notifications | Firebase Cloud Messaging | Push notifications for overdue fees, low attendance, approvals, task reminders, placement updates | FCM project, APNs-equivalent Android credentials, and topic/token strategy decided early |
| Security | HTTPS, bcrypt, JWT, audit log | Transport encryption; password hashing; stateless auth; append-only audit ledger | Security baseline (OWASP ASVS Level 2 targets) established in Sprint 1 |
| DevOps | GitHub Actions | CI/CD: automated test, lint, build, deploy on each release; branch protection rules | Pipeline configured in Sprint 0; every feature branch gated on green CI before merge |

### 2.2 Architectural Building Blocks

2.2.1 Multi-Tenancy & Branch Isolation

Every domain-level table (students, leads, fees, batches, staff, assets, expenses, placements) carries a mandatory branch_id foreign key. A Laravel global scope, activated by middleware, rewrites every query to filter by the branch context derived from the authenticated user's token. Super Admin role bypasses the scope to obtain consolidated views. This approach is cheaper to deliver than database-per-tenant and adequate for a single-institute multi-branch model.

2.2.2 Authentication & Authorization

Authentication is stateless JWT. Authorization is a two-layer RBAC system: (a) role-level permissions (Super Admin, Branch Admin, HR, Finance, Sales, Trainer, Student) define coarse module access; (b) module-level ACLs (View / Add / Edit / Delete) provide fine-grained control. Permissions are resolved server-side on every request; the React frontend hides UI elements cosmetically but never relies on client-side gating for security.

2.2.3 Shared Services (Cross-Cutting)

- Audit Log Service — append-only table capturing actor, action, entity type, entity id, before-state, after-state, timestamp, IP — invoked from a Laravel observer on every create/update/delete.

- Notification Service — unified interface to FCM (push), SMS provider, and SMTP; queue-backed via Laravel Queues + Redis.

- File Service — wraps S3 (or GCP Storage) with signed URLs for document uploads (offer letters, ID proofs, student photos, study materials).

- PDF Service — fee receipts, payroll slips, reports; rendered server-side via dompdf or equivalent.

- Reporting Service — materialised view layer for dashboard KPIs to keep list screens fast under load.

2.2.4 Mobile Architecture

The two Flutter apps (Student and Staff) share a common internal package containing authentication, API client, data models, notification handlers, and utility widgets. Each app is a thin UI layer over this shared core, packaged as a separate Android APK / AAB with its own Firebase project (or at minimum its own FCM topic). Offline-friendly caching (Hive or SharedPreferences) is used for attendance marking and schedule viewing when connectivity is intermittent.

2.2.5 Environments & Deployment

| Environment | Purpose | Data | Deployment Trigger |
| --- | --- | --- | --- |
| Development | Active engineering; daily integration | Synthetic seed data | Push to any feature branch |
| Staging / UAT | Client demos, end-of-phase UAT, pre-prod rehearsal | Masked production snapshot | Merge to develop branch; manual approval for staging promotion |
| Production | Live Dreamzone operations | Real client data; daily snapshot backups; 30-day PITR | Tag + manual approval from release manager |

### 2.3 Non-Functional Requirements Driving Sprint Scope

| Category | Target | Where it is engineered |
| --- | --- | --- |
| Availability | 99.9% monthly uptime SLA | Multi-AZ RDS, auto-scaling EC2, health checks, CloudWatch alarms (Sprint 9 hardening) |
| Performance | List pages < 1.5s p95; API < 400ms p95 | DB indexing strategy, Redis caching, pagination, N+1 query elimination (baked into every feature sprint) |
| Security | OWASP ASVS L2 baseline; bcrypt; HTTPS-only; CSRF; input validation; rate limiting | Security baseline in Sprint 1; penetration test in Sprint 9 |
| Auditability | Every create/edit/delete logged with actor, timestamp, before/after | Cross-cutting observer pattern, implemented in Sprint 1 platform foundations |
| Backup & DR | Daily automated snapshots + 30-day point-in-time recovery | RDS configuration + verified restore drill in Sprint 9 |
| Scalability | Comfortably handle 10× current branch / student count over 3 years | Stateless API, horizontal scaling, S3 for files, indexed queries |
| Observability | Centralised logs, error tracking, uptime monitoring | CloudWatch + Sentry + UptimeRobot configured in Sprint 1 |

# 3. Epic Breakdown

The PDD scope has been decomposed into 14 epics. Epics EP-01 through EP-03 are platform foundations that every feature epic depends on. Epics EP-04 through EP-12 map one-to-one to PDD functional modules. Epics EP-13 and EP-14 cover the two mobile applications. This decomposition gives us a clean dependency graph that sequences the sprint roadmap.

### 3.1 Epic Inventory

| Epic ID | Epic Name | PDD Reference | Type | Priority |
| --- | --- | --- | --- | --- |
| EP-01 | Platform Foundations (CI/CD, Infra, DB, Auth Skeleton) | Section 3 — Tech Stack & Hosting | Foundation | Must |
| EP-02 | Identity, RBAC & Audit Log | Section 2.7.5 | Foundation | Must |
| EP-03 | Branch Management & Multi-Tenancy | Section 2.1 | Foundation | Must |
| EP-04 | Lead Management (Marketing + Pipeline) | Section 2.3 | Feature | Must |
| EP-05 | Student Management & Lifecycle | Section 2.4 | Feature | Must |
| EP-06 | Training Management (Course, Batch, Attendance, Feedback) | Section 2.5 | Feature | Must |
| EP-07 | Accounts — Fees Management | Section 2.8.1 | Feature | Must |
| EP-08 | Accounts — Expenses Management | Section 2.8.2 | Feature | Must |
| EP-09 | HR Management (Directory, Attendance, Payroll, KRA/KPI) | Section 2.7 | Feature | Must |
| EP-10 | Inventory — Stock + Asset + Ticketing | Section 2.6 | Feature | Must |
| EP-11 | Placement Management & Alumni | Section 2.9 | Feature | Must |
| EP-12 | Dashboard, Analytics & Notifications | Section 2.2 + cross-cutting | Feature | Must |
| EP-13 | Staff Android Mobile Application (Flutter) | Section 2.10 | Mobile | Must |
| EP-14 | Student Android Mobile Application (Flutter) | Section 2.10 | Mobile | Must |

### 3.2 Epic Dependency Map

The dependency chain below is the primary driver of sprint sequencing. An epic cannot start until every epic it lists as a prerequisite has reached at least a demo-able state.

| Epic | Depends on | Rationale |
| --- | --- | --- |
| EP-01 Platform Foundations | — (starting point) | Must be first; nothing ships without infra, repo, pipeline |
| EP-02 Identity & RBAC | EP-01 | Needs DB schema, migrations, deployment target |
| EP-03 Branch & Multi-Tenancy | EP-01, EP-02 | Branch scoping is built into the auth/ACL layer |
| EP-04 Lead Management | EP-02, EP-03 | Needs roles (Sales), branch context, auth |
| EP-05 Student Management | EP-02, EP-03, EP-04 | Lead-to-student conversion requires Lead module |
| EP-06 Training Management | EP-05 | Batches enrol students; feedback and attendance depend on student records |
| EP-07 Fees Management | EP-05, EP-06 | Fee plans tie to students and batches |
| EP-08 Expenses | EP-02 | Standalone; needs only RBAC and approval flow |
| EP-09 HR Management | EP-02, EP-03 | Staff directory needs roles and branches |
| EP-10 Inventory / Assets | EP-03, EP-09 | Asset assignment to branches and staff |
| EP-11 Placement | EP-05, EP-06 | Placed students derive from the graduated student pool |
| EP-12 Dashboard & Analytics | All feature epics | Aggregates data across modules; must follow them |
| EP-13 Staff Mobile App | EP-04, EP-06, EP-09 | Needs Lead, Attendance, and Staff APIs |
| EP-14 Student Mobile App | EP-05, EP-06, EP-07, EP-11 | Needs Student, Attendance, Fees, Placement APIs |

### 3.3 Estimated Epic Effort (T-Shirt Sizing)

T-shirt sizes below are based on comparable EiBS projects. These inform capacity planning in Section 4 and are re-calibrated after Sprint 1 actuals.

| Epic | Size | Indicative Story Points | Primary Contributors |
| --- | --- | --- | --- |
| EP-01 Platform Foundations | M | 21 | DevOps, Backend Lead, Frontend Lead |
| EP-02 Identity, RBAC & Audit | L | 34 | Backend, Frontend |
| EP-03 Branch & Multi-Tenancy | M | 21 | Backend, Frontend |
| EP-04 Lead Management | L | 40 | Backend, Frontend, QA |
| EP-05 Student Management | L | 34 | Backend, Frontend, QA |
| EP-06 Training Management | XL | 55 | Backend, Frontend, QA |
| EP-07 Fees Management | L | 40 | Backend, Frontend, QA |
| EP-08 Expenses Management | M | 21 | Backend, Frontend, QA |
| EP-09 HR Management | XL | 55 | Backend, Frontend, QA |
| EP-10 Inventory & Assets | L | 34 | Backend, Frontend, QA |
| EP-11 Placement | M | 21 | Backend, Frontend, QA |
| EP-12 Dashboard & Notifications | L | 40 | Backend, Frontend, QA |
| EP-13 Staff Mobile App | L | 40 | Mobile, Backend, QA |
| EP-14 Student Mobile App | L | 40 | Mobile, Backend, QA |
| Total | — | ~496 SP | Full team |

# 4. Sprint Roadmap

The project delivers in 10 two-week sprints (20 weeks total), starting with a Sprint 0 inception. Each sprint produces a shippable increment deployed to staging, demonstrated to Dreamzone, and (after Phase 2) available for early user feedback. The sprints below are the committed plan; stories may be re-prioritised at each sprint-planning session within the fixed scope anchor.

## Sprint 0 (Inception)  —  Discovery, Setup & Architecture Blueprint

Duration: Week 1–2  ·  2 weeks

Sprint Goal:  Land the team on shared technical and operational ground: finalise architecture decisions, stand up environments, lock the backlog and Definition of Done, and ship a hello-world deployment through the full CI/CD pipeline.

Features Delivered

- No end-user features. This is an enablement sprint producing infrastructure, tooling, and agreements that every subsequent sprint depends on.

- Deployable skeleton application (Laravel API + React shell + Flutter skeleton) running in the staging environment behind HTTPS.

Epics in Play

- EP-01 Platform Foundations (primary)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-001 | As the Delivery Manager, I want a finalised Product Backlog with every PDD requirement traced to a user story so that scope is unambiguous and auditable. | 3 | Backlog in Jira with REQ-ID trace matrix signed off by client |
| DZ-002 | As the Tech Lead, I want a documented Architecture Decision Record (ADR) set so that downstream choices (multi-tenancy, auth, caching) are deliberate and reviewable. | 5 | ADRs for auth, multi-tenancy, DB schema approach, deployment topology committed to repo |
| DZ-003 | As a Developer, I want repositories, branch protection, and a CI pipeline so that no code merges without tests and linting passing. | 5 | GitHub org + 3 repos live; PR checks enforced; main branch protected |
| DZ-004 | As a Developer, I want dev/staging/prod AWS environments provisioned via Terraform so that infrastructure is reproducible. | 8 | Terraform state in S3; three environments running; VPC, RDS, EC2, S3 provisioned |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-001 | Provision Jira project; import backlog; configure sprint board, swim lanes, and workflow states | Delivery Manager |
| TECH-002 | Create 3 GitHub repos: ims-web (React), ims-api (Laravel), ims-mobile (Flutter monorepo) | Tech Lead |
| TECH-003 | Configure branch protection (require PR, 1 approver, green CI) on all repos | Tech Lead |
| TECH-004 | Write Terraform modules: VPC, subnets, security groups, RDS (MySQL 8), EC2 ASG, S3 buckets, CloudFront | DevOps Engineer |
| TECH-005 | Build GitHub Actions pipelines: lint → unit test → build → deploy (dev auto, staging on tag, prod on manual approval) | DevOps Engineer |
| TECH-006 | Bootstrap Laravel 11 API skeleton with JWT auth scaffold (tymon/jwt-auth) and basic health-check endpoint | Backend Lead |
| TECH-007 | Bootstrap React + TypeScript + Vite + Tailwind + React Router skeleton with protected-route pattern | Frontend Lead |
| TECH-008 | Bootstrap Flutter workspace with shared internal package for auth, API client, models | Mobile Lead |
| TECH-009 | Author database migration baseline: users, roles, permissions, branches, audit_log tables | Backend Dev |
| TECH-010 | Draft and circulate Definition of Ready and Definition of Done for the programme | Delivery Manager |
| TECH-011 | Set up Sentry (error tracking), CloudWatch log groups, UptimeRobot probes | DevOps Engineer |
| TECH-012 | Configure Firebase project, create Android app entries, generate google-services.json for each app | Mobile Lead |
| TECH-013 | Agree API contract conventions: REST resource naming, error envelope, pagination, filtering | Tech Lead + Backend + Frontend |
| TECH-014 | Design system kickoff: tokens, colour palette, typography, base components in Storybook | Frontend Lead + Designer |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-001 | Define overall test strategy: unit, integration, E2E (Cypress), API contract (Postman/Newman), mobile (Flutter widget + integration), manual UAT | QA Lead |
| QA-002 | Create Jira test-case repository structure; agree severity/priority taxonomy | QA Lead |
| QA-003 | Stand up Cypress in the web repo with a smoke test against the deployed skeleton | QA Engineer |
| QA-004 | Stand up Postman/Newman collection in ims-api with health-check test running in CI | QA Engineer |
| QA-005 | Walk through the Definition of Done with the whole team and sign it off | QA Lead + Delivery Manager |

Dependencies & Prerequisites

| Dependency | Description / Action Required |
| --- | --- |
| Client input | Branding assets (logos, colours, fonts), sample course/batch data, existing operational glossary |
| Client input | AWS account ownership decision — EiBS-managed or Dreamzone-owned account with IAM access |
| Client input | Domain name for the web application; ownership of Firebase project for long-term handover |
| Tooling | Jira, GitHub Organisation, Figma, Sentry accounts procured and licensed |
| Decision | Signed PDD and Statement of Work; advance instalment received (per PDD Section 4) |

## Sprint 1  —  Identity, RBAC, Branch Management & Audit Foundations

Duration: Week 3–4  ·  2 weeks

Sprint Goal:  Deliver the security and tenancy spine of the whole platform: working login, role-based access control enforced at both API and UI, branch CRUD, and the audit logger that every downstream feature will hook into.

Features Delivered

- Web login and password reset flow (PDD §3 security baseline).

- Super Admin can create, edit, and deactivate branches (PDD §2.1).

- Super Admin can create users, assign them to roles and a branch (PDD §2.7.5).

- Every create/edit/delete is recorded in the audit log (PDD §3 — full audit trail).

Epics in Play

- EP-01 Platform Foundations (continuation)

- EP-02 Identity, RBAC & Audit Log (primary)

- EP-03 Branch Management (primary)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-010 | As a registered user, I want to log in with my email and password so that I can access the system securely. | 3 | JWT issued; bcrypt hash; 5-fail lockout; HTTPS only |
| DZ-011 | As a user who forgot my password, I want to reset it via email so that I regain access without admin help. | 3 | Time-boxed reset token; email sent via SMTP; token single-use |
| DZ-012 | As a Super Admin, I want to create, edit, and deactivate branches so that each physical location has its own data context. | 5 | Branch CRUD with unique code; deactivated branches hide in pickers but preserve historical data |
| DZ-013 | As a Super Admin, I want to create users and assign them to roles and a branch so that access rights are correct from day one. | 5 | User created with temp password; role + branch bound; welcome email sent |
| DZ-014 | As a Super Admin, I want to manage the role-to-permission matrix so that I can grant or revoke module access per role. | 8 | Matrix UI; permissions stored; changes take effect on next token refresh |
| DZ-015 | As a Branch Admin, I want to see only my branch's data so that I am not distracted by irrelevant records. | 5 | Global query scope enforced; Super Admin can override; integration tests cover bypass attempts |
| DZ-016 | As a Compliance Officer, I want every create/edit/delete logged with actor, timestamp, before/after so that all actions are traceable. | 5 | Audit log table + Eloquent observer; viewable by Super Admin; immutable from app layer |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-020 | Implement auth endpoints: POST /auth/login, /auth/logout, /auth/refresh, /auth/forgot, /auth/reset | Backend Dev A |
| TECH-021 | Write Laravel middleware: JwtAuthenticate, RoleAuthorize, BranchScopeBinding | Backend Dev A |
| TECH-022 | Build role-permission schema: roles, permissions, role_permission, user_role tables with seeder for 7 default roles | Backend Dev B |
| TECH-023 | Build Branch CRUD API: GET/POST/PUT/PATCH /branches with validation and pagination | Backend Dev B |
| TECH-024 | Implement Laravel global scope for branch_id filtering; make bypassable for Super Admin only | Backend Lead |
| TECH-025 | Implement AuditLogObserver; register on all domain models; store JSON before/after diff | Backend Lead |
| TECH-026 | React login page + password reset flow with form validation and error states | Frontend Dev A |
| TECH-027 | React auth context + token refresh logic + axios interceptor | Frontend Dev A |
| TECH-028 | React Branch Management screen: list, create, edit, deactivate with confirmation modals | Frontend Dev B |
| TECH-029 | React User Management screen with role picker and branch picker | Frontend Dev B |
| TECH-030 | React Role-Permission Matrix screen (grid of modules × CRUD checkboxes) | Frontend Dev B |
| TECH-031 | React route guard component: hides unauthorised routes and UI elements based on token claims | Frontend Lead |
| TECH-032 | Audit Log viewer screen with filters by actor, date, entity, action | Frontend Dev A |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-010 | Write Postman regression suite for all auth and user endpoints; integrate into Newman CI run | QA Engineer |
| QA-011 | Negative-path testing: expired tokens, wrong role, branch-crossing attempts, SQL injection payloads | QA Engineer + Security Champion |
| QA-012 | Verify password storage is bcrypt with appropriate cost factor; verify no plaintext anywhere in logs | Security Champion |
| QA-013 | Cypress E2E tests: full login → create branch → create user → login as that user flow | QA Engineer |
| QA-014 | Audit log verification: confirm every CRUD on Branch and User populates audit_log with correct diff | QA Engineer |
| QA-015 | Accessibility smoke: keyboard-only login, screen-reader labels on form fields (WCAG 2.1 AA) | QA Engineer |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| SMTP provider | Transactional email service (AWS SES, SendGrid, or similar) credentials required for password reset |
| Prior sprint | All Sprint 0 infrastructure must be green; skeleton deployed to staging |
| Client input | Confirmation of the 7 roles and their exact permission set — sample matrix circulated for sign-off |

## Sprint 2  —  Lead Management — Marketing Tracker & Sales Pipeline

Duration: Week 5–6  ·  2 weeks

Sprint Goal:  Deliver the complete Lead Management module so the sales team can capture leads from any source, track the full New → Converted pipeline, log follow-ups, and schedule reminders — with the lead-to-student bridge stubbed ready for Sprint 3.

Features Delivered

- Marketing event planner with list and calendar views (PDD §2.3.1).

- Lead capture with source auto-tagging and assignment to sales executives (PDD §2.3.2).

- Status pipeline: New → Contacted → Interested → Follow-up → Converted / Lost.

- Follow-up notes log, call-log sync, reminder engine.

- One-click Convert to Student placeholder (target record created in Sprint 3 module).

Epics in Play

- EP-04 Lead Management (primary, completed this sprint)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-020 | As a Marketing Executive, I want to create marketing events with date, venue, campaign details so that campaigns are tracked centrally. | 3 | Event CRUD; required fields validated; branch-scoped |
| DZ-021 | As a Marketing Executive, I want to log leads generated per source and event so that campaign ROI is measurable. | 3 | Lead counts per source stored and editable |
| DZ-022 | As a Marketing Executive, I want a calendar view of events so that I can see scheduling conflicts at a glance. | 5 | Month/week/day views; click-to-edit; drag-to-reschedule |
| DZ-023 | As a Sales Executive, I want to capture a lead with name, phone, email, source, interest area so that no enquiry is lost. | 3 | Lead created; source tag auto-applied; duplicate phone warning |
| DZ-024 | As a Sales Manager, I want to assign leads to individual sales executives so that ownership is clear. | 3 | Bulk assign + single assign; notification sent to assignee |
| DZ-025 | As a Sales Executive, I want to progress a lead through the pipeline with status updates so that management sees real-time conversion metrics. | 5 | Status transitions validated; reason-for-loss required on Lost |
| DZ-026 | As a Sales Executive, I want to log follow-up notes and call outcomes so that history is preserved across team handovers. | 5 | Timestamped, user-stamped notes; call-log entries with duration + outcome |
| DZ-027 | As a Sales Executive, I want to schedule a reminder for a future action so that follow-ups don't slip. | 5 | Reminder engine with cron; in-app + email notification; snooze option |
| DZ-028 | As a Sales Executive, I want a one-click Convert to Student button so that I don't retype the lead's details. | 5 | Lead marked Converted; payload handed to Student module (stub API until Sprint 3) |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-040 | Design database tables: marketing_events, lead_sources, leads, lead_notes, lead_call_logs, lead_reminders | Backend Dev A |
| TECH-041 | Build REST endpoints for all Lead domain objects; apply branch scope and RBAC | Backend Dev A |
| TECH-042 | Implement reminder engine: Laravel scheduler + queue worker dispatching notifications | Backend Dev B |
| TECH-043 | Implement call-log normaliser — accept JSON from any future CRM/dialer integration | Backend Dev B |
| TECH-044 | Implement Convert-to-Student endpoint producing a hand-off payload with all lead fields | Backend Lead |
| TECH-045 | React Marketing Events list + calendar (use react-big-calendar) | Frontend Dev A |
| TECH-046 | React Lead Pipeline kanban board with drag-to-change-status | Frontend Dev A |
| TECH-047 | React Lead detail drawer: profile, notes, call logs, reminders, action buttons | Frontend Dev B |
| TECH-048 | React Lead import CSV (bulk) with preview + validation | Frontend Dev B |
| TECH-049 | Wire notifications: new assignment → in-app bell + email | Backend Dev B + Frontend |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-020 | Test pipeline state machine: all valid and invalid transitions; ensure no orphan states | QA Engineer |
| QA-021 | Test reminder engine: timezone correctness, snooze, overdue surfacing, idempotent re-delivery | QA Engineer |
| QA-022 | Verify branch isolation on leads: Branch A Sales cannot see Branch B leads in any API or UI path | QA Engineer |
| QA-023 | Cypress E2E: full New → Follow-up → Converted journey, including note logging and reminder scheduling | QA Engineer |
| QA-024 | Performance test: 10,000 synthetic leads — list pagination returns < 1.5s p95 | QA Engineer |
| QA-025 | CSV import edge cases: duplicate phones, malformed rows, UTF-8 characters, Excel vs CSV delimiters | QA Engineer |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprint | Sprint 1 must deliver roles, branches, users, audit log — blocking dependency |
| Client input | List of lead sources to seed (social media, referrals, walk-ins, events, etc.) |
| Client input | Sales team structure — flat roster or hierarchical teams |
| Risk | Notification spam — tune batching and quiet-hours defaults before first real user uses the system |

## Sprint 3  —  Student Management & Lifecycle

Duration: Week 7–8  ·  2 weeks

Sprint Goal:  Close the Lead → Student bridge and deliver the full Student module: list, profile, document storage, materials log, payment schedule view, and trainer assignment — making Dreamzone's single source of student truth a reality.

Features Delivered

- Full student lifecycle record, seeded either via Convert-to-Student or direct admission (PDD §2.4).

- Student list with search, filter, sort (branch, course, batch, status).

- Student profile: personal details, documents, photo, materials, sessions placeholder, staff assignment.

- Payment schedule view surface (actual fee engine lands in Sprint 5).

Epics in Play

- EP-05 Student Management (primary, completed this sprint)

- EP-04 Lead Management (closing the Convert hand-off)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-030 | As a Branch Admin, I want to create a student directly so that walk-in admissions without a prior lead can still be captured. | 3 | Student CRUD with validation; mandatory branch and enrolment date |
| DZ-031 | As a Sales Executive, I want Convert-to-Student to auto-populate a draft student record so that no data is re-entered. | 5 | Draft record opens with lead fields pre-filled; finalise button commits |
| DZ-032 | As a Branch Admin, I want a Student List with filters (branch, course, batch, status) so that I can find any student in under 10 seconds. | 5 | Indexed search; server-side pagination; URL-persisted filters |
| DZ-033 | As a Branch Admin, I want to upload student documents and photo so that records are complete and portable. | 5 | S3-backed uploads with signed URLs; file-type and size validation; virus scan stub |
| DZ-034 | As a Branch Admin, I want to log materials distributed to each student so that dispatches are auditable. | 5 | Materials log per student with item, quantity, date, acknowledging staff |
| DZ-035 | As a Trainer, I want to see the students assigned to my batches so that I know who I'm teaching. | 3 | Student list scoped by trainer role shows only their batches' students |
| DZ-036 | As a Branch Admin, I want to view the payment schedule section on the profile so that financial status is visible alongside student data. | 3 | Read-only embed from (upcoming) Fees module; placeholder populated from a stub service |
| DZ-037 | As a Branch Admin, I want to change student status (Active / On Hold / Dropped-out / Graduated) so that reporting reflects the current roster. | 3 | Status change captured in audit log with reason |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-060 | DB schema: students, student_documents, student_materials, student_status_history | Backend Dev A |
| TECH-061 | Student REST API with filters, pagination, sort; includes the stub for Convert ingestion | Backend Dev A |
| TECH-062 | File upload service wrapping S3: presigned POST URLs, content-type whitelist, max-size config | Backend Dev B |
| TECH-063 | Implement full-text search index (MySQL FULLTEXT or MeiliSearch) for student name/email/phone | Backend Dev B |
| TECH-064 | React Student List with server-driven filters and CSV export | Frontend Dev A |
| TECH-065 | React Student Profile: tabbed UI — Overview / Documents / Materials / Sessions / Payments / Staff | Frontend Dev A |
| TECH-066 | React Document Uploader with progress bar, preview, delete | Frontend Dev B |
| TECH-067 | React Convert-to-Student draft screen with pre-filled fields and diff against source lead | Frontend Dev B |
| TECH-068 | Stub payment schedule API returning canned data (replaced in Sprint 5) | Backend Lead |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-030 | End-to-end Lead → Convert → Student → edit → change status flow with audit trail verification | QA Engineer |
| QA-031 | File upload tests: max size, forbidden types, large-file streaming, network interruption recovery | QA Engineer |
| QA-032 | Branch isolation: documents stored under branch-scoped S3 prefix; cross-branch access blocked | QA Engineer + Security Champion |
| QA-033 | Performance: 50,000 synthetic students — filter+search responds within target; export completes | QA Engineer |
| QA-034 | Accessibility: tab-order, ARIA labels, error focus management on the Student Profile tabs | QA Engineer |
| QA-035 | Data migration dry-run: sample import of legacy student spreadsheet from Dreamzone | QA Engineer + BA |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprint | Sprint 2 Convert-to-Student hand-off payload — blocking |
| Client input | Sample student CSV from existing Excel workbooks for migration dry-run |
| Client input | Confirmed document categories (ID proof types, academic certificates, photograph spec) |
| Risk | Storage costs — confirm S3 lifecycle policy (Infrequent Access after 90 days, Glacier after 2 years) |

## Sprint 4  —  Training Management — Courses, Batches & Enrolment

Duration: Week 9–10  ·  2 weeks

Sprint Goal:  Deliver the training-delivery backbone: course design with curriculum, batch creation and scheduling, student enrolment into batches, and staff assignment. Attendance and feedback follow in Sprint 5.

Features Delivered

- Course catalogue with title, description, duration, fee, category, and structured curriculum (PDD §2.5.1).

- Batch creation with start/end date, timing, mode (online/offline/hybrid), capacity (PDD §2.5.2).

- Course-to-batch mapping.

- Student-to-batch enrolment with seat availability check.

- Staff-to-batch assignment (primary trainer, co-trainer, support staff).

Epics in Play

- EP-06 Training Management (primary, part 1 of 2)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-040 | As a Branch Admin, I want to create a course with title, description, duration, fee, and category so that it can be offered to students. | 3 | Course CRUD with category taxonomy; draft/published states |
| DZ-041 | As a Curriculum Lead, I want to structure a course into modules → topics → sub-topics with content and links so that the curriculum is transparent to students and trainers. | 8 | Nested structure editor; drag-to-reorder; links validated; preview mode |
| DZ-042 | As a Branch Admin, I want to create a batch with dates, timing, mode, and capacity so that training delivery is scheduled. | 5 | Batch CRUD; validation on overlaps and capacity; branch-scoped |
| DZ-043 | As a Branch Admin, I want to link a batch to a specific course so that curriculum and fee are inherited. | 3 | One-to-one batch→course link; cannot change once enrolment starts |
| DZ-044 | As a Branch Admin, I want to enrol students into batches with seat availability checks so that over-booking is prevented. | 5 | Seat capacity enforced; waiting-list optional; bulk enrol CSV |
| DZ-045 | As a Branch Admin, I want to assign primary trainer, co-trainer, and support staff to a batch so that delivery responsibility is clear. | 5 | Staff picker filters by role and availability; conflict check against other batches |
| DZ-046 | As a Trainer, I want to see my batch list with students and schedule so that I can prepare for sessions. | 3 | Trainer-scoped batch list; read-only roster |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-080 | DB schema: courses, curriculum_modules, curriculum_topics, batches, batch_enrollments, batch_staff | Backend Dev A |
| TECH-081 | Course REST API with nested curriculum endpoints (/courses/:id/modules/:id/topics) | Backend Dev A |
| TECH-082 | Batch REST API with overlap validation (same room, same trainer) and seat-capacity guard | Backend Dev B |
| TECH-083 | Bulk enrolment endpoint accepting student ID list; returns per-student success/failure | Backend Dev B |
| TECH-084 | Staff-availability query: given date range, which staff have bandwidth | Backend Lead |
| TECH-085 | React Course Catalogue with card/list toggle | Frontend Dev A |
| TECH-086 | React Curriculum Builder with drag-and-drop tree editor | Frontend Dev A |
| TECH-087 | React Batch Wizard: course pick → schedule → capacity → staff assignment, with validation on each step | Frontend Dev B |
| TECH-088 | React Batch Detail: tabs for Overview / Curriculum / Students / Staff / Sessions (sessions tab populated in Sprint 5) | Frontend Dev B |
| TECH-089 | Notification: trainer assigned to a new batch receives in-app + email alert | Backend Dev B |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-040 | Capacity enforcement: concurrent enrolment attempts at capacity boundary (race condition test) | QA Engineer |
| QA-041 | Staff conflict detection: same trainer on overlapping batches, across branches too | QA Engineer |
| QA-042 | Curriculum builder: deep-nesting, reorder, delete-with-children, undo/redo behaviour | QA Engineer |
| QA-043 | End-to-end: create course → build curriculum → create batch → assign trainer → enrol 50 students → trainer sees roster | QA Engineer |
| QA-044 | Migration test: import a sample legacy batch roster and confirm fidelity | QA Engineer + BA |
| QA-045 | UAT demo dry-run with Dreamzone Academics lead: walk them through the full flow before sprint review | BA + QA Lead |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprint | Sprint 3 Student module — blocking for enrolment functionality |
| Client input | Course catalogue master list; curriculum content for at least 2 real courses for UAT |
| Client input | Rules for batch naming convention (e.g., DZ-WEB-2026-01) |
| Risk | Curriculum builder UX complexity — plan a dedicated design review in sprint mid-point to de-risk |

## Sprint 5  —  Attendance, Feedback & Fees Collection

Duration: Week 11–12  ·  2 weeks

Sprint Goal:  Close out Training Management by delivering class-by-class attendance and post-session feedback, and stand up the Fees module so revenue collection, receipts, and automated reminders can begin operating end-to-end.

Features Delivered

- Class-by-class student attendance marking on the web (PDD §2.5.3).

- Post-session feedback with star ratings and comments; batch-wise aggregate ratings.

- Fee plan creation (full pay, EMI, custom instalments) and student assignment (PDD §2.8.1).

- Fee collection with PDF/print receipt generation; payment-mode tracking.

- Automated overdue-payment reminders (email + in-app).

Epics in Play

- EP-06 Training Management (completion — attendance & feedback)

- EP-07 Fees Management (primary, completed this sprint)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-050 | As a Trainer, I want to mark attendance class-by-class so that the academic record is accurate. | 5 | Roster view; bulk mark all present; per-student override; timestamp |
| DZ-051 | As a Branch Admin, I want monthly attendance summaries per batch so that low-attendance alerts can be acted on. | 3 | Summary report; CSV export; threshold-based colour coding |
| DZ-052 | As a Student (or parent), I want to submit a session feedback form with stars and comments so that teaching quality is measurable. | 3 | 1–5 stars; text field; one submission per student per session |
| DZ-053 | As a Branch Admin, I want batch-wise aggregate ratings so that trainer performance is visible. | 3 | Avg rating, count, distribution chart per batch |
| DZ-054 | As a Finance Officer, I want to create fee plans (full pay / EMI / custom) so that any payment arrangement can be supported. | 5 | Plan templates; per-student override; instalment schedule generated |
| DZ-055 | As a Finance Officer, I want to record a fee payment and generate a printable PDF receipt so that students get proof instantly. | 5 | Receipt PDF with Dreamzone branding; sequential receipt number; mode captured |
| DZ-056 | As a Finance Officer, I want payment mode tracking (cash, UPI, bank transfer, cheque) so that reconciliation with bank statements is possible. | 3 | Mode enum with optional reference number (UPI txn, cheque no., UTR) |
| DZ-057 | As a Student, I want automated overdue-payment reminders so that I don't miss deadlines. | 5 | Daily cron; escalating schedule (T-3, T, T+3, T+7); email + in-app |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-100 | DB schema: sessions, attendance_records, session_feedback, fee_plans, fee_schedules, fee_payments, receipts | Backend Dev A |
| TECH-101 | Attendance API with bulk-mark endpoint; writes to attendance_records with unique (session, student) constraint | Backend Dev A |
| TECH-102 | Feedback API with one-per-student-per-session guard; aggregation endpoint for batch summaries | Backend Dev B |
| TECH-103 | Fee-plan engine: generate instalment schedule from plan template + enrolment date | Backend Lead |
| TECH-104 | Payment-record API; on-save generates receipt record and triggers PDF service | Backend Lead |
| TECH-105 | PDF receipt template (dompdf) with branding, receipt number, GST fields (if applicable) | Backend Dev B |
| TECH-106 | Reminder scheduler: Laravel command + cron entry; idempotent resend guard | Backend Dev B |
| TECH-107 | React Session Attendance screen optimised for tablet use; offline-safe save-on-reconnect | Frontend Dev A |
| TECH-108 | React Feedback form (student-facing) + Admin aggregate view with charts | Frontend Dev A |
| TECH-109 | React Fee Plan editor; per-student plan override view on Student profile | Frontend Dev B |
| TECH-110 | React Payment Capture modal with receipt preview and print/download | Frontend Dev B |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-050 | Attendance idempotency: re-submitting the same roster must not duplicate records | QA Engineer |
| QA-051 | Feedback one-per-student constraint: both UI and API block second submission | QA Engineer |
| QA-052 | Fee-plan arithmetic: EMI calculation across edge cases (1, 12, 24 instalments; partial months) | QA Engineer |
| QA-053 | PDF receipt validation: content, branding, receipt number sequence unbroken, print quality | QA Engineer + Design |
| QA-054 | Reminder engine: T-3 / T / T+3 / T+7 cadence; quiet-hours; holiday skip configuration | QA Engineer |
| QA-055 | Replace Sprint 3's stub payment-schedule API with real data; regression test Student Profile page | QA Engineer |
| QA-056 | Financial reconciliation scenario: record 20 payments across modes; verify totals match expected | QA Engineer + Finance Stakeholder |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprints | Sprints 3 and 4 — Student and Batch/Session records must be real, not stubs |
| Client input | Existing receipt template and receipt-number format; GST / tax configuration if applicable |
| Client input | Overdue reminder cadence policy; sample of current manual reminder wording |
| Risk | Receipt-number uniqueness during concurrent payments — handled with DB sequence or advisory lock |
| Risk | PDF rendering quality across browsers — confirm on Chrome + Firefox + Safari |

## Sprint 6  —  HR Management — Directory, Attendance, Leave, Payroll, KRA/KPI

Duration: Week 13–14  ·  2 weeks

Sprint Goal:  Deliver the complete HR module — staff directory with documents, daily attendance, leave management, attendance-linked payroll, and the KRA/KPI appraisal framework. This is the largest functional sprint and will require full team focus.

Features Delivered

- Staff directory with personal info, designation, department, branch, joining date, salary (PDD §2.7.1).

- Staff document storage (offer letters, ID proofs, certifications).

- Daily staff attendance with manual entry and app-based check-in option (PDD §2.7.2).

- Leave calendar update by HR.

- Monthly attendance summary reports.

- KRA/KPI definition per role with manager review and rating (PDD §2.7.3).

- Monthly payroll generation with attendance-linked calculations; payroll summary reports (PDD §2.7.4).

Epics in Play

- EP-09 HR Management (primary, completed this sprint)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-060 | As an HR Manager, I want to create and maintain staff profiles so that all employee data is centralised. | 3 | Staff CRUD; salary stored encrypted at rest; branch-scoped |
| DZ-061 | As an HR Manager, I want to upload staff documents by category so that compliance paperwork is retrievable. | 3 | Category-tagged uploads; expiry reminders for time-bound docs |
| DZ-062 | As an HR Manager, I want to mark daily staff attendance manually so that remote or exceptional cases are covered. | 3 | Roster grid by date; bulk present / half-day / leave codes |
| DZ-063 | As a Staff Member, I want to check in via the Staff mobile app so that attendance is captured without HR intervention. | 5 | Geofence-optional check-in endpoint; today's status visible in app (app UI in Sprint 8) |
| DZ-064 | As an HR Manager, I want to update leave details on a calendar so that the team has shared visibility. | 5 | Leave type, dates, approval status; calendar view; conflict check |
| DZ-065 | As an HR Manager, I want monthly attendance summary reports so that payroll inputs are reliable. | 3 | Per-staff totals: present / absent / half / leave; CSV export |
| DZ-066 | As an HR Manager, I want to define KRAs and KPIs per role so that appraisals are structured and measurable. | 5 | Role → KRA → KPI tree; target values; weightage |
| DZ-067 | As a Manager, I want to review and rate my reports on their KPIs so that appraisals are documented. | 5 | Review form per reportee; rating scale configurable; signed-off reviews locked |
| DZ-068 | As an HR Manager, I want to generate monthly payroll with attendance-linked calculations so that salary disbursement is accurate. | 8 | Payroll engine reading attendance + salary + leave; edit-and-approve workflow; summary export |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-120 | DB schema: staff, staff_documents, staff_attendance, leave_records, kras, kpis, kpi_reviews, payroll_runs, payroll_lines | Backend Dev A |
| TECH-121 | Staff CRUD API with encrypted-at-rest salary column (Laravel casts with AES key in KMS) | Backend Dev A |
| TECH-122 | Attendance + leave APIs with calendar aggregation endpoint | Backend Dev B |
| TECH-123 | KRA/KPI configuration API with per-role template and per-user customisation | Backend Dev B |
| TECH-124 | Payroll engine: deterministic rules; dry-run vs. commit; summary export (CSV + PDF) | Backend Lead |
| TECH-125 | Mobile check-in API endpoint (consumed by Staff app in Sprint 8) | Backend Lead |
| TECH-126 | React Staff Directory with filters and multi-select actions | Frontend Dev A |
| TECH-127 | React Staff Profile with tabs: Personal / Documents / Attendance / Leave / KPI / Payroll history | Frontend Dev A |
| TECH-128 | React Attendance Roster (month grid editable by HR) | Frontend Dev B |
| TECH-129 | React Leave Calendar with drag-to-create range | Frontend Dev B |
| TECH-130 | React KRA/KPI configurator (role-first, staff-second) | Frontend Dev B |
| TECH-131 | React Payroll Run screen: preview → edit lines → commit → export | Frontend Dev A |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-060 | Salary-data confidentiality: verify encrypted at rest; verify only Super Admin / HR role sees it | Security Champion + QA |
| QA-061 | Payroll arithmetic: 20 synthetic staff with varied attendance + leave; expected totals match to the rupee | QA Engineer + Finance |
| QA-062 | Payroll edempotency: committed runs cannot be modified; re-runs require a new period | QA Engineer |
| QA-063 | Leave calendar conflict handling: overlapping leaves, public holidays, half-day markings | QA Engineer |
| QA-064 | KPI review workflow: draft → submitted → acknowledged → locked state transitions | QA Engineer |
| QA-065 | Document expiry reminders trigger at T-30, T-7, T+0, T+7 | QA Engineer |
| QA-066 | Performance: payroll run for 100 staff must complete in < 30 seconds | QA Engineer |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprint | Sprint 1 RBAC (roles, users, branches) — blocking |
| Client input | Final payroll rules: components, deductions (PF/ESI/TDS), leave accrual policy, working-days calendar |
| Client input | Final KRA/KPI template for each role; sample review cycle the team can dry-run against |
| Risk | Payroll complexity and statutory compliance — confirm if this is full payroll or gross-only; factor in a payroll SME review in sprint mid-point |
| Risk | HR data privacy — encryption-at-rest and access audit must be demonstrated for client comfort |

## Sprint 7  —  Inventory, Assets, Ticketing, Expenses & Placement

Duration: Week 15–16  ·  2 weeks

Sprint Goal:  Deliver the remaining web-administration modules — Inventory (stock + assets + ticketing), Expenses with approval workflow, and the Placement module including alumni migration and placed-student tracking.

Features Delivered

- Stock management: items, categories, quantity, supplier, cost (PDD §2.6.1).

- Material distribution log to students with acknowledgment.

- Low-stock alerts with reorder thresholds.

- Asset register with unique ID, category, location, warranty (PDD §2.6.2).

- Asset assignment to branches, departments, staff.

- Ticketing system: Raised → Assigned → In Progress → Resolved.

- Expense capture by category and approval workflow (PDD §2.8.2).

- Alumni auto-migration, interview event management, placed-student tracker (PDD §2.9).

Epics in Play

- EP-10 Inventory — Stock + Asset + Ticketing (primary)

- EP-08 Expenses Management (primary)

- EP-11 Placement Management (primary)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-070 | As a Branch Admin, I want to add stock items with category, quantity, cost, and supplier so that consumables are tracked. | 3 | Stock CRUD; unit of measurement; supplier master |
| DZ-071 | As a Branch Admin, I want to log material distribution with student acknowledgment so that dispatches are auditable. | 3 | Link to Student; signed-by stamp; updates stock balance |
| DZ-072 | As a Branch Admin, I want low-stock alerts so that I reorder before running out. | 3 | Threshold per item; daily cron alert; in-app + email |
| DZ-073 | As an IT Admin, I want to maintain an asset register with location and warranty so that physical assets are trackable. | 3 | Unique asset ID; QR-code generation; warranty reminder |
| DZ-074 | As a Staff Member, I want to raise a ticket for a faulty asset so that issues are resolved quickly. | 5 | Ticket form with asset picker; status workflow; SLA timer |
| DZ-075 | As an IT Admin, I want a ticket queue with assignment and status transitions so that workload is managed. | 3 | Kanban; filter by status; reassignment history logged |
| DZ-076 | As a Requester, I want to submit an expense with category and receipt upload so that reimbursement is on record. | 3 | Expense form; receipt S3 upload; category picker |
| DZ-077 | As a Manager, I want to approve or reject expenses so that finance only processes authorised items. | 3 | Approval queue; comment on reject; notification chain |
| DZ-078 | As a Finance Officer, I want month-wise and category-wise expense reports so that budget tracking is straightforward. | 3 | Pivot report; CSV export; trend chart |
| DZ-079 | As a Placement Officer, I want graduated students to auto-migrate to the alumni pool so that placement activity continues seamlessly. | 3 | On status=Graduated, mirror record in alumni table; preserve course history |
| DZ-080 | As a Placement Officer, I want to create interview events so that recruitment drives are coordinated. | 3 | Event CRUD with company, date, role, eligibility |
| DZ-081 | As a Placement Officer, I want to record placed students with company, role, CTC, joining date so that outcome metrics are captured. | 3 | Placement record linked to alumnus; CTC and offer letter upload |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-140 | DB schema: stock_items, stock_movements, assets, asset_assignments, tickets, expenses, expense_approvals, alumni, interview_events, placements | Backend Dev A |
| TECH-141 | Inventory APIs: stock CRUD, distribute, low-stock query | Backend Dev A |
| TECH-142 | Asset APIs with QR-code generation via server-side library | Backend Dev B |
| TECH-143 | Ticket state-machine API with SLA clock and reassignment | Backend Dev B |
| TECH-144 | Expense workflow: submit → approve/reject → paid state; configurable approver matrix | Backend Lead |
| TECH-145 | Alumni migration job triggered on status=Graduated; idempotent | Backend Lead |
| TECH-146 | Placement APIs for interview events and placed-student records | Backend Dev A |
| TECH-147 | React Stock screen + distribution modal | Frontend Dev A |
| TECH-148 | React Asset screen with QR preview and print labels | Frontend Dev A |
| TECH-149 | React Ticket Kanban + detail drawer | Frontend Dev B |
| TECH-150 | React Expense submission + Approval queue + report | Frontend Dev B |
| TECH-151 | React Placement screens (Alumni / Events / Placed Tracker) | Frontend Dev A |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-070 | Stock reconciliation: sequence of additions + distributions equals current balance to the unit | QA Engineer |
| QA-071 | Asset QR flow: generate, print, scan (manual) — confirm correct asset is resolved | QA Engineer |
| QA-072 | Ticket SLA: breach triggers escalation to the configured manager | QA Engineer |
| QA-073 | Expense approval matrix: multi-level workflow, delegation, rejection comments | QA Engineer |
| QA-074 | Alumni migration: graduate 10 students in one batch — all land in alumni with correct course data | QA Engineer |
| QA-075 | Placement data privacy: only Placement and Admin roles see CTC figures | Security Champion |
| QA-076 | Regression: full platform suite run (auth, lead, student, batch, fee, HR, inventory) — all previous sprints still green | QA Lead |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprints | All domain modules (Student, Batch, Staff) must be stable — regression window consumes ~15% of capacity |
| Client input | Existing asset register (spreadsheet) for import; supplier master data |
| Client input | Expense-approval hierarchy per branch; category list |
| Risk | Sprint scope is wide — three modules in one sprint. Mitigation: trim ticketing SLA automation to a follow-up item if capacity slips |

## Sprint 8  —  Dashboard, Notifications & Staff Mobile Application

Duration: Week 17–18  ·  2 weeks

Sprint Goal:  Deliver the role-sensitive executive dashboard with customisable widgets, finalise the notification fabric across email / in-app / push, and ship the Staff Android application with its full feature set.

Features Delivered

- Role-sensitive dashboard with widgets for leads, admissions, revenue, attendance, HR (PDD §2.2).

- Alerts for pending reminders, approvals, deadlines.

- Graphical card-view reports: enrolment, revenue, placement.

- Unified notification centre: overdue fees, low attendance, approvals (PDD §3 automated notifications).

- Staff Android app: schedule, mark attendance, update lead status, receive notifications, raise queries (PDD §2.10).

Epics in Play

- EP-12 Dashboard, Analytics & Notifications (primary)

- EP-13 Staff Android Mobile Application (primary, completed this sprint)

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-090 | As a Super Admin, I want a consolidated dashboard of leads, admissions, revenue, attendance, HR so that I see institute health at a glance. | 5 | Widgets lazy-load; role-sensitive; branch selector for Super Admin |
| DZ-091 | As a Branch Admin, I want a dashboard filtered to my branch so that I focus only on my operations. | 3 | Same widgets, branch scope enforced |
| DZ-092 | As a User, I want an alert bell for pending reminders, approvals, deadlines so that nothing is missed. | 3 | Unread count; mark-all-read; drill into item |
| DZ-093 | As a Trainer, I want the Staff app to show my daily schedule so that I plan my day from my phone. | 3 | Today view + 7-day outlook; offline cache |
| DZ-094 | As a Trainer, I want to mark student attendance from the Staff app so that I'm not tied to a desktop. | 5 | Roster list; bulk mark; offline-safe with sync on reconnect |
| DZ-095 | As a Sales Executive, I want to update lead status and log calls from the Staff app so that field work is captured immediately. | 5 | Lead detail view; status change; call-log entry with one-tap dial |
| DZ-096 | As a Staff Member, I want push notifications for tasks and reminders so that I respond on time. | 3 | FCM integration; deep-link to relevant screen; notification settings screen |
| DZ-097 | As a Staff Member, I want to raise a query so that HR or Admin can respond. | 3 | Free-form query form with category; status updates by HR |
| DZ-098 | As a Staff Member, I want to check in for attendance from the Staff app so that the manual process is eliminated. | 5 | Calls the Sprint-6 check-in endpoint; device time + optional geo |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-160 | Dashboard aggregation API: materialised views for leads_by_week, revenue_by_month, etc. — cached 15 min | Backend Lead |
| TECH-161 | Notification service completion: in-app bell, unread markers, Preferences screen | Backend Dev A |
| TECH-162 | React Dashboard with widget framework (draggable cards where feasible) | Frontend Lead |
| TECH-163 | React chart components (Recharts) for enrolment, revenue, placement | Frontend Dev A |
| TECH-164 | Flutter Staff App — auth, navigation scaffold, theming via shared internal package | Mobile Dev A |
| TECH-165 | Flutter Staff App — Today/Schedule screen pulling from Batch Session API | Mobile Dev A |
| TECH-166 | Flutter Staff App — Attendance screen with offline queue (Hive) and reconnect sync | Mobile Dev B |
| TECH-167 | Flutter Staff App — Lead Pipeline screen with status update and call-log | Mobile Dev B |
| TECH-168 | Flutter Staff App — FCM push integration, notification tray, deep-linking | Mobile Lead |
| TECH-169 | Flutter Staff App — Check-in / Raise-Query screens | Mobile Dev A |
| TECH-170 | Android build config, code-signing, Play Internal Testing track setup | Mobile Lead + DevOps |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-080 | Dashboard data accuracy: sample 5 widgets against manually computed numbers — must match | QA Engineer + BA |
| QA-081 | Dashboard performance: first paint under 2s; widget refresh under 1s | QA Engineer |
| QA-082 | Notification delivery: push, email, in-app all reach the right audience; suppression on opt-out | QA Engineer |
| QA-083 | Staff app regression on 5 Android models (Android 10, 11, 12, 13, 14; small + large screens) | QA Engineer (Mobile) |
| QA-084 | Staff app offline-attendance: mark attendance airplane-mode → reconnect → records sync without duplicates | QA Engineer (Mobile) |
| QA-085 | Staff app deep-links: tap notification → correct screen opens, auth preserved | QA Engineer (Mobile) |
| QA-086 | Battery and data usage profiling — ensure app is not a background drain | QA Engineer (Mobile) |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprints | All feature modules (Sprints 2–7) must expose stable APIs — breaking changes forbidden from this point |
| Tooling | Google Play Console access; Android keystore; Firebase project with FCM credentials |
| Client input | Staff device estimate for procurement / BYOD decision; minimum Android version target (recommend 10+) |
| Risk | Parallelism: web Dashboard and Mobile app run in parallel — a mobile-track drop in capacity delays Sprint 9. Mitigation: dedicated mobile pair from Sprint 0 |

## Sprint 9  —  Student Mobile App, UAT, Hardening & Production Launch

Duration: Week 19–20  ·  2 weeks

Sprint Goal:  Ship the Student Android application, complete end-to-end UAT with Dreamzone key users, run the security and performance hardening pass, execute data migration, and go live. This is the release sprint — no new scope enters.

Features Delivered

- Student Android app: enrolled courses & sessions, attendance records, fee schedule, materials, feedback, placement updates, push notifications (PDD §2.10).

- Production go-live with data migration from legacy Excel sources.

- Security hardening: penetration test findings remediated; OWASP ASVS L2 checklist closed.

- Operational runbooks, admin manual, and user training videos handed over.

Epics in Play

- EP-14 Student Android Mobile Application (primary, completed this sprint)

- Platform hardening across all prior epics

- Handover and training

User Stories

| Story ID | User Story | SP | Acceptance Criteria (summary) |
| --- | --- | --- | --- |
| DZ-100 | As a Student, I want to see my enrolled courses and upcoming sessions so that I never miss a class. | 3 | Today + upcoming; colour-coded by course |
| DZ-101 | As a Student, I want to view my attendance record so that I know where I stand. | 3 | Per-course percentage; date-wise list |
| DZ-102 | As a Student, I want to see my fee schedule and payment status so that I plan payments. | 3 | Instalment list; overdue highlighted; receipts downloadable |
| DZ-103 | As a Student, I want to access study materials and resources so that I can learn outside class. | 3 | File list by course/module; open/download; cached for offline read |
| DZ-104 | As a Student, I want to submit session feedback so that my voice reaches the institute. | 3 | Feedback form for today's sessions; one-per-session constraint |
| DZ-105 | As a Student, I want to see placement updates so that I can apply to opportunities. | 3 | Interview events list; eligibility tag; tap to register interest |
| DZ-106 | As a Student, I want push notifications for reminders and events so that I stay informed without opening the app. | 3 | FCM integration; notification settings |
| DZ-107 | As a Dreamzone Admin, I want all legacy student and fee data migrated into the new system so that we start live with complete history. | 8 | Migration scripts run on staging → UAT sign-off → production; reconciliation report |
| DZ-108 | As a Dreamzone User, I want training materials and a user manual so that my team can self-onboard. | 3 | PDF user manual + 8–10 short screencast videos per role |

Technical Tasks

| Task ID | Technical Task | Primary Owner |
| --- | --- | --- |
| TECH-180 | Flutter Student App — scaffold using shared internal package; theming and navigation | Mobile Dev A |
| TECH-181 | Flutter Student App — Courses & Sessions screen | Mobile Dev A |
| TECH-182 | Flutter Student App — Attendance screen (read-only) | Mobile Dev B |
| TECH-183 | Flutter Student App — Fees screen with instalment view and receipt download | Mobile Dev B |
| TECH-184 | Flutter Student App — Materials viewer (PDF/video/link) with offline cache | Mobile Dev A |
| TECH-185 | Flutter Student App — Feedback + Placement Updates screens | Mobile Dev B |
| TECH-186 | Flutter Student App — FCM push + notification settings + deep-linking | Mobile Lead |
| TECH-187 | Student App Play Store listing, icons, screenshots, privacy policy link, Internal Testing release | Mobile Lead + DevOps |
| TECH-188 | Data migration: write Laravel console commands to import legacy Excel sources into production schema | Backend Lead |
| TECH-189 | Penetration test remediation: address all High and Medium findings from engagement run in mid-sprint | Backend Lead + Security Champion |
| TECH-190 | Production DNS cutover, SSL certs, CloudWatch alarms, PagerDuty/on-call rota | DevOps |
| TECH-191 | Backup and restore drill on production RDS; document RPO/RTO actuals | DevOps |
| TECH-192 | Write admin runbook (deployment, rollback, restore, user unlock, common incidents) | DevOps + Tech Lead |
| TECH-193 | Record training videos (1 per role × 7 roles; 3–5 min each) | BA + Trainer (EiBS) |
| TECH-194 | On-site go-live support, Day-1 floor walking, hypercare handoff | Delivery Manager + BA |

QA / Testing Activities

| QA ID | QA / Testing Activity | Owner |
| --- | --- | --- |
| QA-090 | Student app regression across device matrix (5 devices × 2 Android versions min) | QA Engineer (Mobile) |
| QA-091 | Full UAT with Dreamzone — 3 sessions × 3 hours: Admin, Teaching, Finance/HR tracks | QA Lead + BA |
| QA-092 | End-to-end persona scenarios: 'A day in the life' for each of the 8 personas | QA Lead |
| QA-093 | Penetration test by external vendor — OWASP Top 10, authn/authz, API fuzzing, mobile-specific checks | External security firm |
| QA-094 | Performance test: 100 concurrent users on key flows (login, dashboard, payment capture, attendance mark) | QA Engineer |
| QA-095 | Backup-restore drill: kill staging DB, restore from snapshot, verify integrity | QA + DevOps |
| QA-096 | Data migration reconciliation: row counts, financial totals, spot-check of 100 students | QA + BA + Finance Stakeholder |
| QA-097 | Accessibility audit (WCAG 2.1 AA) on top 15 screens | QA Engineer |
| QA-098 | Production smoke test on Day-0; formal go-live sign-off checklist | QA Lead + Delivery Manager |

Dependencies & Risks for This Sprint

| Dependency | Description / Action Required |
| --- | --- |
| Prior sprints | All scope from Sprints 0–8 is code-complete; no new features admitted; bug-fix only from now |
| External | Booked penetration test vendor (scheduled 2 weeks before sprint start) |
| Client input | UAT user availability calendar; data migration source files locked 10 days before go-live |
| Client input | Play Store developer account ownership (recommended: Dreamzone-owned with EiBS as maintainer) |
| Risk | UAT defects — reserve 30% sprint capacity unplanned for bug-fix; any P1/P2 open blocks go-live |
| Risk | Migration fidelity — rehearse twice on staging before production; finance lead must sign off |

# 5. Development Timeline

The plan calls for 10 two-week sprints (including Sprint 0 inception) — approximately 20 calendar weeks or 5 months end-to-end from project kickoff to production go-live. This is expressed below as a consolidated timetable.

### 5.1 Sprint-by-Sprint Summary

| Sprint | Weeks | Theme | Key Output / Shippable Increment |
| --- | --- | --- | --- |
| 0 (Inception) | 1–2 | Discovery & Setup | Environments, CI/CD, skeleton app deployed; backlog + ADRs signed off |
| 1 | 3–4 | Identity, RBAC, Branches, Audit | Working login, branch CRUD, user + role management, audit log |
| 2 | 5–6 | Lead Management | Marketing tracker + Sales pipeline + reminders; Convert-to-Student stub |
| 3 | 7–8 | Student Management | Full student module with documents, materials, payment schedule view |
| 4 | 9–10 | Training — Courses & Batches | Course catalogue, curriculum builder, batches, enrolment, staff assignment |
| 5 | 11–12 | Attendance, Feedback, Fees | Class attendance, session feedback, fee plans, receipts, overdue reminders |
| 6 | 13–14 | HR Management | Staff directory, attendance, leave, KRA/KPI, payroll |
| 7 | 15–16 | Inventory, Expenses, Placement | Stock, assets, tickets, expenses, alumni, placement tracker |
| 8 | 17–18 | Dashboard + Staff Mobile App | Role-sensitive dashboard, notifications, Staff Android app live on Internal Testing |
| 9 | 19–20 | Student App + UAT + Launch | Student Android app, UAT, hardening, migration, production go-live |

### 5.2 Phase-Level Rollup

Sprints consolidate naturally into four delivery phases that align with the PDD's stated phased-delivery model. Each phase ends with a working, deployed increment to staging and a client demo.

| Phase | Sprints | Calendar | Phase Deliverable |
| --- | --- | --- | --- |
| Phase 1 — Foundations | 0 + 1 | Weeks 1–4 | Infrastructure, auth, RBAC, branches, audit. Internal demo only. |
| Phase 2 — Student Journey Core | 2 + 3 + 4 + 5 | Weeks 5–12 | Lead → Student → Batch → Attendance → Fees. First external demo and Phase-2 go-live on staging. |
| Phase 3 — Operations & HR | 6 + 7 | Weeks 13–16 | HR, Payroll, Inventory, Expenses, Placement. Second external demo. |
| Phase 4 — Mobile, Dashboard & Launch | 8 + 9 | Weeks 17–20 | Dashboard, both mobile apps, UAT, migration, production go-live. |

### 5.3 Delivery Ceremonies & Cadence

| Ceremony | Frequency | Purpose | Attendees |
| --- | --- | --- | --- |
| Sprint Planning | Start of each sprint (2 hrs) | Commit to sprint backlog; refine stories | Full team + Product Owner |
| Daily Stand-up | Daily (15 min) | Progress, blockers, day's focus | Delivery team |
| Backlog Refinement | Mid-sprint (1 hr) | Ready the next sprint's stories to DoR | PO, Tech Lead, QA Lead |
| Sprint Review / Demo | End of sprint (1.5 hrs) | Demonstrate increment; collect feedback | Full team + Dreamzone stakeholders |
| Sprint Retrospective | End of sprint (1 hr) | Continuous improvement | Delivery team |
| Client Steering | Fortnightly (30 min) | Scope, risks, dependencies, timeline | Delivery Manager + Dreamzone project sponsor |
| Weekly Progress Report | Every Friday (written) | Per PDD §1 commitment | Circulated to Dreamzone leadership |

### 5.4 Important Note on the Vendor-Stated Timeline

The PDD cover page states a 9-week timeline across 4 phases. This execution plan instead commits to 20 weeks (10 sprints × 2 weeks). The rationale is captured as a formal risk item — R-01 — in Section 6. In short: delivering 10 web modules plus 2 Android applications at professional quality, with adequate UAT and hardening, is not achievable in 9 weeks for a cross-functional team of this size; compressing the schedule would force cuts in testing, security, documentation, or scope. The 20-week plan is the responsible delivery horizon we recommend committing to jointly with Dreamzone.

# 6. Risks & Dependencies

The risks below are maintained in a living risk register reviewed at every fortnightly steering meeting. Each item has an owner, a mitigation plan, and a trigger signal. The highest-priority risk, R-01, relates directly to the timeline discrepancy between the PDD's stated 9-week window and the 20-week plan in Section 5.

### 6.1 Risk Register

| ID | Risk | Likelihood | Impact | Mitigation / Plan | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Timeline discrepancy: PDD states 9-week delivery; realistic estimate is 20 weeks for the full 10-module + 2-mobile scope. Silently compressing will sacrifice quality and/or scope. | High | High | Table this openly with Dreamzone at kickoff. Agree one of three paths: (a) commit to 20 weeks; (b) reduce scope (e.g., defer Inventory, KRA/KPI, or one mobile app to Phase 2); (c) accept a quality floor explicitly. Decision recorded in writing before Sprint 1. | Delivery Manager |
| R-02 | Payroll statutory compliance (PF, ESI, TDS) exceeds the PDD's scope of 'attendance-linked calculations'. Scope ambiguity may surface during Sprint 6. | Medium | High | Clarify in Sprint 0 whether PDD §2.7.4 covers gross payroll only or full statutory compliance. If the latter, raise a change request or integrate a specialised payroll module. | BA + Tech Lead |
| R-03 | Data migration fidelity from fragmented Excel workbooks — messy source data will extend Sprint 9 and may cause go-live slip. | High | High | Begin migration discovery in Sprint 3; run two full dry-runs on staging (Sprint 7 and Sprint 9 mid-point); finance lead signs off reconciliation reports. | BA + Backend Lead |
| R-04 | Android device fragmentation and minimum version commitment not yet defined — may drive rework late in Sprint 8/9. | Medium | Medium | Commit to Android 10+ (~95% coverage) in Sprint 0 ADR; test on 5 representative devices from Sprint 8 onwards. | Mobile Lead |
| R-05 | Scope creep — small additions like 'one more report' across 10 modules can consume 20% of total capacity. | High | Medium | Strict change-control process via Steering Committee; any new scope triggers a written impact assessment; fixed-price anchor defended. | Delivery Manager |
| R-06 | Role-permission matrix ambiguity — PDD lists 7 roles but exact module-by-module rights undefined. | High | Medium | Draft matrix in Sprint 0; signed off before Sprint 1. Treat as a hard precondition for the RBAC epic. | BA |
| R-07 | UAT user availability during Sprint 9 — Dreamzone staff running day operations may not have bandwidth for 3 × 3-hour UAT sessions. | Medium | High | Lock UAT calendar in Sprint 6; remote UAT option as backup; record sessions for absentees. | Delivery Manager |
| R-08 | External penetration test slot availability — booking 4–6 weeks ahead is typical. | Medium | Medium | Book the vendor in Sprint 4; backup internal review using OWASP ZAP if external slip. | Tech Lead |
| R-09 | Third-party integrations not yet specified (SMS gateway, payment gateway beyond receipts) — surprise scope if requested mid-project. | Medium | Medium | Confirm in Sprint 0 what integrations are in scope. Any new integration is a change request. | BA |
| R-10 | Reliance on a single Tech Lead / Mobile Lead — key-person risk. | Low | High | Pair programming enforced on critical paths; ADRs and runbooks keep context transferable. | Delivery Manager |
| R-11 | Cloud cost overrun — AWS bills can surprise without budget alarms. | Low | Medium | Set CloudWatch billing alarms in Sprint 0; weekly cost review; right-size instances post-load-test. | DevOps |
| R-12 | Flutter Android-only per PDD — if iOS is requested later, effort is not a small delta, it's a re-plan. | Low | Medium | Re-confirm Android-only in Sprint 0 ADR. iOS, if requested later, is a new SOW. | Delivery Manager |

### 6.2 External Dependencies

| # | Dependency | Required By | Status / Action |
| --- | --- | --- | --- |
| D-01 | AWS account ownership decision (EiBS-managed vs Dreamzone-owned) | Sprint 0 | To confirm in kickoff |
| D-02 | Production domain name and SSL strategy | Sprint 0 | Client to provide or delegate procurement |
| D-03 | Firebase project with FCM credentials | Sprint 0 (infra), Sprint 8 (staff app) | To be created and handed over |
| D-04 | Google Play Developer account | Sprint 8 (staff), Sprint 9 (student) | Client to hold or authorise EiBS as maintainer |
| D-05 | SMTP / transactional email provider (AWS SES, SendGrid) | Sprint 1 | Credentials required for password reset and notifications |
| D-06 | SMS gateway credentials (optional per PDD) | Sprint 2 if SMS notifications confirmed in scope | Scope to confirm |
| D-07 | Payment gateway (if online payments are in scope beyond receipt printing) | Sprint 5 if confirmed | Scope to confirm |
| D-08 | Legacy data sources — Excel workbooks for students, fees, staff | Sprint 3 onwards | Staged extracts requested weeks before needed |
| D-09 | Branding assets — logo, colour palette, typography | Sprint 0 | Figma brand kit to be shared |
| D-10 | Signed Statement of Work and advance instalment | Sprint 0 start | Per PDD commercial terms |
| D-11 | External penetration test vendor booking | Sprint 9 mid-point | Engaged in Sprint 4 |
| D-12 | Dreamzone subject-matter experts for UAT | Sprint 9 | Calendar locked in Sprint 6 |

### 6.3 Blockers to Watch

- Unsigned role-permission matrix entering Sprint 1 — will block all subsequent feature work that relies on authorisation.

- Unresolved payroll scope entering Sprint 6 — risk of late re-planning of one of the largest sprints.

- Missing legacy data samples entering Sprint 3 — migration complexity cannot be assessed without them.

- No finalised receipt and PDF template entering Sprint 5 — blocks Fee receipt UAT.

- No Play Store account ownership entering Sprint 8 — blocks Staff app Internal Testing release.

# 7. Recommended Team Roles

The following cross-functional team composition is recommended for the 20-week delivery. The numbers reflect full-time-equivalent allocation; smaller teams are feasible but extend the timeline proportionately.

### 7.1 Core Team Composition

| Role | FTE | Primary Responsibilities | Key Sprints |
| --- | --- | --- | --- |
| Delivery Manager / Scrum Master | 0.5 | Sprint planning, ceremonies, risk register, client steering, release management | All |
| Product Owner / BA | 0.75 | Backlog ownership, requirement clarification, acceptance criteria, UAT coordination, training material | All |
| Tech Lead / Architect | 1.0 | ADRs, architectural integrity, code review, cross-cutting concerns, deployment gate-keeping | All |
| Backend Engineer (Laravel) — Senior | 1.0 | API design, multi-tenancy, audit log, hardest modules (fees, payroll, RBAC) | All |
| Backend Engineer (Laravel) — Mid | 1.0 | Feature APIs, integrations, test coverage | Sprints 1–9 |
| Frontend Engineer (React/TS) — Senior | 1.0 | Design system, routing, shared components, toughest screens | All |
| Frontend Engineer (React/TS) — Mid | 1.0 | Feature screens, forms, tables, charts | Sprints 1–9 |
| Mobile Engineer (Flutter) — Lead | 1.0 | Shared package, auth, FCM, Play Store release, hardest app screens | Sprints 0, 4–9 (ramping) |
| Mobile Engineer (Flutter) | 1.0 | Feature screens, offline handling, platform integrations | Sprints 7–9 (peak) |
| QA Lead | 0.5 | Test strategy, UAT, regression gate-keeping, sign-off checklists | All |
| QA Engineer — Web / API | 1.0 | Cypress E2E, Postman regression, manual exploratory | All |
| QA Engineer — Mobile | 0.5 | Flutter widget + integration tests; device-farm manual testing | Sprints 7–9 (peak) |
| DevOps Engineer | 0.5 | Terraform, CI/CD, environments, observability, backups, release automation | All (heavy at bookends) |
| UI/UX Designer | 0.5 | Wireframes, high-fidelity mockups, design review, accessibility | Heaviest in Sprints 0–3; reviews thereafter |
| Security Champion | 0.25 | Threat modelling, security review per epic, penetration test liaison | All |

### 7.2 Indicative Full-Time-Equivalent Summary

| Discipline | Total FTE | Notes |
| --- | --- | --- |
| Product / Delivery / BA | 1.25 | Orchestration and requirements |
| Engineering — Backend | 3.0 | Lead + 2 developers |
| Engineering — Frontend | 2.0 | Lead + 1 developer |
| Engineering — Mobile | 2.0 | Ramps during Sprints 7–9; lower load earlier |
| Quality Assurance | 2.0 | Lead + Web QA + Mobile QA (part-time overlap) |
| DevOps / Security | 0.75 | Shared resource; front-loaded and back-loaded |
| Design | 0.5 | Concentrated in early sprints |
| Total core team | ~11.5 FTE | Peak; steady-state ~9 FTE |

### 7.3 Responsibility Assignment (Abbreviated RACI)

R = Responsible · A = Accountable · C = Consulted · I = Informed

| Deliverable | Delivery Mgr | Tech Lead | Backend | Frontend | Mobile | QA | DevOps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint planning & commitment | A/R | C | C | C | C | C | I |
| Architecture decisions (ADRs) | I | A/R | C | C | C | I | C |
| API design & build | I | A | R | C | C | C | I |
| UI build & integration | I | C | C | A/R | I | C | I |
| Mobile app build & release | I | C | C | I | A/R | C | C |
| Test strategy & execution | I | C | C | C | C | A/R | I |
| CI/CD, infra, observability | I | A | C | I | I | C | R |
| UAT, go-live, training | A/R | C | C | C | C | R | C |
| Security baseline & pen-test | I | A | R | C | C | C | R |
| Data migration | A | C | R | I | I | R | C |

# Appendix A — PDD Requirement to Epic Traceability

Every functional requirement described in PDD Section 2 is mapped to at least one epic below. Traceability matrices at the user-story level are maintained in Jira.

| PDD Ref | Functional Area | Epic(s) | Primary Sprint(s) |
| --- | --- | --- | --- |
| 2.1 | Branch Management | EP-03 | Sprint 1 |
| 2.2 | Dashboard | EP-12 | Sprint 8 |
| 2.3.1 | Marketing Tracking | EP-04 | Sprint 2 |
| 2.3.2 | Lead Pipeline & Conversion | EP-04 | Sprint 2 |
| 2.4 | Student Management | EP-05 | Sprint 3 |
| 2.5.1 | Course Management | EP-06 | Sprint 4 |
| 2.5.2 | Schedule & Batch Management | EP-06 | Sprint 4 |
| 2.5.3 | Attendance & Feedback | EP-06 | Sprint 5 |
| 2.6.1 | Materials Stock Management | EP-10 | Sprint 7 |
| 2.6.2 | Asset Management + Ticketing | EP-10 | Sprint 7 |
| 2.7.1 | Staff Directory | EP-09 | Sprint 6 |
| 2.7.2 | Staff Attendance | EP-09 | Sprint 6 |
| 2.7.3 | KRA/KPI Performance Management | EP-09 | Sprint 6 |
| 2.7.4 | Payroll Management | EP-09 | Sprint 6 |
| 2.7.5 | User Roles & Privileges | EP-02 | Sprint 1 |
| 2.8.1 | Fees Management | EP-07 | Sprint 5 |
| 2.8.2 | Expenses Management | EP-08 | Sprint 7 |
| 2.9 | Placement Management | EP-11 | Sprint 7 |
| 2.10 (Staff) | Staff Mobile Application | EP-13 | Sprint 8 |
| 2.10 (Student) | Student Mobile Application | EP-14 | Sprint 9 |
| §3 Audit Log | Cross-cutting audit trail | EP-02 | Sprint 1 (engineered), all (applied) |
| §3 Automated Notifications | Cross-cutting notifications | EP-12 | Sprint 2 (bootstrapped), Sprint 8 (completed) |
| §3 Multi-branch Architecture | Cross-cutting multi-tenancy | EP-03 | Sprint 1 |
| §3 RBAC | Cross-cutting authorisation | EP-02 | Sprint 1 |

# Appendix B — Definition of Ready & Definition of Done

### Definition of Ready (a story is ready to be pulled into a sprint)

- User story is written in the As-a / I-want / So-that format with a clear user persona.

- Acceptance criteria are listed and testable.

- Dependencies on other stories, modules, or external inputs are identified.

- Designs (wireframes or mocks) attached where applicable.

- Story is estimated in story points by the team.

- Story is small enough to complete in a single sprint (split if not).

- Linked to a PDD requirement ID for traceability.

### Definition of Done (a story is done)

- Code merged to the develop branch via approved pull request.

- Unit tests written and passing; code coverage does not drop.

- API tests (for backend stories) pass in the Newman/Postman suite.

- E2E tests (for user-facing flows) updated or added; Cypress suite passes in CI.

- Security checklist for the story (input validation, authn/authz, logging) reviewed and met.

- Deployed to the development environment, then promoted to staging for UAT.

- Acceptance criteria verified by QA; story accepted by Product Owner.

- Documentation (API spec, user-facing notes) updated.

- Audit log entries verified for any create/edit/delete the story introduces.

# Appendix C — Document Control

| Version | Date | Author | Summary |
| --- | --- | --- | --- |
| v1.0 | 21 April 2026 | EiBS Global Delivery Team | Initial Agile Sprint Execution Plan derived from PDD EIBS-DZ-IMS-2025-001. |

Elysian Intelligence Business Solutions  ·  EiBS Global

info@eibsglobal.com  ·  Technology that Elevates